# सार्वजनिक खरिद ऐन, २०६३ को दफा ६५ को उपदफा (१) को खण्ड (ग) ले दिएको अधिकार बमोजिम सार्वजनिक खरिद अनुगमन कार्यालयबाट जारी गरिएको

(Issued by the Public Procurement Monitoring Office in accordance with the authority given by clause (c) of Subsection (1) of Section 65 of the Public Procurement Act, 2063)

STANDARD BIDDING DOCUMENT (SBD)

Procurement of Works

International Competitive Bidding (ICB)

[Single-Stage: Two Envelope Bidding procedure]

Government of Nepal

Office of The Prime Minister and Council of Ministers

Public Procurement Monitoring Office (PPMO)

(Revised on August 2026)

(Revised on 12 August 2026)

Preface

This Standard Bidding Document (SBD) for Procurement of Works has been prepared by the Government of Nepal (GoN), Public Procurement Monitoring Office (PPMO) to facilitate post-qualification bidding procedures used for the procurement of works through International Competitive Bidding (ICB).

The SBD includes; a format for the Invitation of Bids, Bidding Procedures, Requirements and Conditions of Contract and Contract Forms.

While using the SBD, the following directions should be considered.

- No change should be made to the wording of the Section 1, Instructions to Bidders (ITB) and Section 7, General Conditions of Contract. All provisions related to a particular contract or contracts should be stated/included in other relevant sections of the Document.

- The attached information forms may require minor adaptation to suit the individual requirements of particular contract.

- The italicized footnotes and remarks in the SBD are not part of the text. They contain guidance and instruction for the Agencies preparing the document.

If any provisions of this document are inconsistent with Public Procurement Act (PPA), 2063 or Public Procurement Regulations (PPR), 2064, the provision of this document shall be void to the extent of such inconsistency and the provision of PPA and PPR shall prevail.

BIDDING DOCUMENT

for

THE PROCUREMENT OF

[Insert identification of the Works]

International Competitive Bidding (ICB)

Single Stage: Two-Envelope Bidding Procedure

(TECHNICAL BID)

[Insert the name of Public Entity]

Issued on:

Invitation for Bids No.:

ICB No.:

Contract Identification No:

Abbreviations

BD........................	Bidding Document

BDF……………...	Bidding Forms

BDS......................	Bid Data Sheet

BOQ ……………..	Bill of Quantities

COF ……………..	Contract Forms

DP ……………….	Development Partners

DoLI ……….	Department of Local Infrastructure

ELI ……………….	Eligibility

EQC.....................	Evaluation and Qualification Criteria

EXP ………………	Experience

FIN ……………….	Financial

GCC.....................	General Conditions of Contract

GoN .....................	Government of Nepal

ICB......................	International Competitive Bidding

ICC....................... 	International Chamber of Commerce

ITB....................... 	Instructions to Bidders

JV ………………..	Joint Venture

LIT ………………..	Litigation

NCB ……………...	National Competitive Bidding

NPR ……………...	Nepalese Rupees

PAN ……………… Permanent Account Number

PPA ……………..	Public Procurement Act

PPMO …………… 	Public Procurement Monitoring Office

PPR ……………...	Public Procurement Regulations

PL.........................	Profit and Loss

SBD...................... 	Standard Bidding Document

SCC ……………..	Special Conditions of Contract

TS......................... 	Technical Specifications

VAT ………………	 Value Added Tax

WRQ ……………..	Works Requirements

Table of Contents

Invitation of bids -------------------------------------------------------------------------	 1

PART I	BIDDING PROCEDURES

Section 1 -	Instructions to Bidders (ITB)	  4

Section 2 -	Bid Data Sheet (BDS) 	  30

Section 3 -	Evaluation and Qualification Criteria (EQC) 	  34

Section 4 -	Bidding Forms (BDF) 	  47

PART II  	EMPLOYER'S REQUIREMENTS

Section 5 -	Works Requirements (WRQ) 	  75

Section 6 -	Preamble to the Bill of Quantities (BOQ) 	  82

PART III	CONDITIONS OF CONTRACT AND CONTRACT FORMS

Section 7 -	General Conditions of Contract (GCC) 	  84

Section 8 -	Special Conditions of Contract (SCC) 	  85

Section 9 -	Contract Forms (COF)	  101

Invitation for Bids

Government of Nepal (GoN)/or other Public Entity if applicable

[Name of Employer]

Invitation for Bids No: __________________

Date of publication: __________________

Name of the Development Partner [if applicable]: ______________________

Loan/Credit/Grant No [if applicable]: ______________________

1. 	[The Government of Nepal [GoN/or other public entity if applicable] has [allocated funds or received a loan/credit/grant] from [GoN/or other public entity if applicable or Development Partner] towards the cost of [Name of Project] and intends to apply part of the funds to cover eligible payments under the Contract for [Name and identification number of Contract]. Bidding is open to all eligible Nepalese and Foreign Bidders.

2. 	[Name of Employer] invites sealed bids or electronic bids from eligible bidders for the construction of [Brief description of the Works] under International Competitive Bidding – Single-Stage; Two Envelope Bidding procedures.

Only eligible bidders with the following key qualifications should participate in this bidding:

Minimum Average Annual Construction Turnover of the best 3 years within the last 10 years:  [enter in NPR or in US$….……………….]

Minimum Work experience of similar size and nature: [number of project and value of each project]

3. 	Eligible Bidders may obtain further information and inspect the Bidding Documents at the office of [Name, location, mailing address, telephone and facsimile numbers and email address of the Employer] or may visit PPMO website www.bolpatra.gov.np/egp.

- A complete set of Bidding Documents may be purchased from the office [insert name and address] and the office [insert name and address] by eligible Bidders on the submission 
of a written application, along with the copy of company/firm registration certificate, and upon 
payment of a non-refundable fee of [Insert amount] till [Insert date]. If so requested, the Bidding Documents can also be sent by post/courier services upon payment of additional cost of NPR. [amount in NPR or in US$]. However, the Employer will not be responsible for delay or non-delivery of the documents so sent. Information to deposit the cost of bidding document in Bank:

Name of the Bank: …………………..

Name of Office: ………………………………..

Office Code no. :……………..

Office Account no.: ……………………….

Rajaswa (revenue) Shirshak no. : ………………………….

Or

Bidder who chooses to submit their bid electronically may download the bidding documents for e-submission from PPMO’s Web Site www.bolpatra.gov.np at no cost.

5.	Pre-bid meeting shall be held at [insert name and address] at [insert time and date].

6.	Sealed or electronic bids must be submitted to the office [Name and address] by hand/courier or through PPMO website www.bolpatra.gov.np/egp. on or before [Time] on [Date]. Bids received after this deadline will be rejected.

7. 	The bids will be opened in the presence of Bidders' representatives who choose to attend at [Time and date] at the office of [Address of office]. Bids must be valid for a period of [Insert number of days] after bid opening and must be accompanied by a bid security or scanned copy of the bid security in pdf format in case of e-bid, amounting to a minimum of [insert amount in NPR or Equivalent US$ (2 to 3 % of estimated amount exclusive VAT and Contingencies but including PS)], which shall be valid for 30 days beyond the validity period of the bid (i.e. [Insert Date])

8. 	If the last date of purchasing and /or submission falls on a government holiday, then the next working day shall be considered as the last date. In such case the validity period of the bid and bid security shall remain the same as specified for the original last date of bid submission.

9.	Other mandatory information as per PPA and PPR.

Note: In case of bid invited for any combination of contract lots, the bidder may submit the bid for one or more lots for which bids are invited and may offer discounts/ cross discounts for different award combinations. Evaluation for each contract lot will be done separately but the decision on contracts award will be based on the bid price combinations that will result in least cost to the Employer.

PART I: BIDDING PROCEDURES

Section 1 - Instructions to Bidders

This section specifies the procedures to be followed by Bidders in the preparation and submission of their Bids. Information is also provided on the submission, opening, and evaluation of bids and on the award of Contract.

Table of Clauses

A.	General	6

1.	Scope of Bid	6

2.	Source of Funds	6

3.	Fraud and Corruption	6

4.	Eligible Bidders	9

5.	Eligible Materials, Equipment and Services	10

B.	Contents of Bidding Document	11

6.	Sections of Bidding Document	11

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting	11

8.	Amendment of Bidding Document	12

C.	Preparation of Bids	12

9.	Cost of Bidding	12

10.	Language of Bid	12

11.	Documents Comprising the Bid	13

12.	Letter of Bid and Schedules	13

13.	Alternative Bids	14

14.	Bid Prices and Discounts	14

15.	Currencies of Bid and Payment	15

16.	Documents Comprising the Technical Proposal	15

17.	Documents Establishing the Qualifications of the Bidder	16

18.	Period of Validity of Bids	16

19.	Bid Security	16

20.	Format and Signing of Bid	17

D.	Submission and Opening of Bids	19

21.	Sealing and Marking of Bids	19

22.	Deadline for Submission of Bids	21

23.	Late Bids	22

24.	Withdrawal, and Modification of Bids	22

25.	Bid Opening	23

E.	Evaluation and Comparison of Bids	24

26.	Confidentiality	24

27.	Clarification of Bids	24

28.	Deviations, Reservations, and Omissions	25

29.	Determination of Responsiveness	25

30.	Nonconformities, Errors, and Omissions	25

31.	Qualification of the Bidder	26

32.	Correction of Arithmetical Errors	26

33.	Conversion to Single Currency	27

34.	Domestic Preference	27

35.	Subcontractors	27

36.	Evaluation of Price Bids	27

37.	Comparison of Bids	28

38.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids	28

F.	Award of Contract	28

39.	Award Criteria	28

40.	Letter of Intent to Award the Contract/ Notification of Award	28

41.	Performance Security	29

42.	Signing of Contract	29

43.	Complain and Review	30

Section 1 - Instructions to Bidders

| General |  |
| --- | --- |
| - Scope of Bid | - In connection with the Invitation for Bids indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this Bidding Document for the procurement of Works as specified in Section 5 (Works Requirements). The name, identification, and number of Contracts of the International Competitive Bidding (ICB) are provided in the BDS. - Throughout this Bidding Document: - the term “in writing” means communicated in written form and delivered against receipt through e-GP system or email or fax or courier; - except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and - “day” means calendar day. |
| - Source of Funds | - GoN Funded: In accordance with its annual program and budget, approved by the GoN, the implementing agency indicated in the BDS plans to apply a portion of the allocated budget toward the cost of the project named in the BDS. The GoN intends to apply a portion of the allocated budget to eligible payments under the contract(s) for which this Bidding Document is issued. Or Public Entities' own Resource Funded: In accordance with its annual program and budget, approved by the public entity, the implementing agency indicated in the BDS plans to apply a portion of the allocated budget to eligible payments under the contract(s) for which this Bidding Document is issued. Or DP Funded: The GoN has applied for or received financing (hereinafter called “funds”) from the Development Partner (hereinafter called “the DP”) indicated in the BDS toward the cost of the project named in the BDS. The GoN intends to apply a portion of the funds to eligible payments under the contract(s) for which this Bidding Document is issued. - DP Funded: Payment by the DP will be made only at the request of the GoN and upon approval by the DP in accordance with the terms and conditions of the financing agreement between the GoN and the DP (hereinafter called the “Loan Agreement”), and will be subject in all respects to the terms and conditions of that Loan Agreement. No party other than the GoN shall derive any rights from the Loan Agreement or have any claim to the funds. |
| - Fraud and Corruption | - The Government of Nepal (GoN) requires that the procuring entities as well as bidders, suppliers, and contractors and their sub-contractors under GoN/DP-financed contracts, shall adhere to the highest standard of ethics during the procurement and execution of such contracts. In this context, the Employer; - defines, for the purposes of this provision, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; - “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; - “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; - “collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party. - “obstructive practice” means: - deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a GoN/DP investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or - acts intended to materially impede the exercise of the GoN’s/DP’s inspection and audit rights provided for under sub-clause 3.5 below. (vi) “integrity violation” is any act which violates Anticorruption Policy, including (i) to (v) above and the following: abuse, conflict of interest, violations of GoN/DP sanctions, retaliation against whistleblowers or witnesses, and other violations of Anticorruption Policy, including failure to adhere to the highest ethical standard. (b) will reject bid(s) if it determines that the bidder has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations in competing for the contract in question; (c) will sanction a firm or individual, including declaring ineligible, for a stated period of time, to be awarded a GoN/DP-financed contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices or other integrity violations in competing for, or in executing, a GoN/DP-financed contract. - The Bidder shall not carry out or cause to carry out the following acts with an intention to influence the implementation of the procurement process or the procurement agreement: - give or propose improper inducement directly or indirectly, - distortion or misrepresentation of facts, - engaging in corrupt or fraudulent practice or involving in such act, - interference in participation of other competing bidders, - coercion or threatening directly or indirectly to cause harm to the person or the property of any person to be involved in the procurement proceedings, - collusive practice among bidders before or after submission of bids for distribution of works among bidders or fixing artificial/uncompetitive bid price with an intention to deprive the Employer the benefit of open competitive bid price, - contacting the Employer with an intention to influence the Employer with regards to the bids or interference of any kind in examination and evaluation of the bids during the period from the time of opening of the bids until the notification of award of contract. - PPMO on the recommendation of the Employer may blacklist a Bidder for a period of one (1) to three (3) years for its conduct including the following grounds and seriousness of the act committed by the bidder: - if convicted by a court of law in a criminal offence which disqualifies the Bidder from participating in the contract, - if it is established that the contract agreement signed by the Bidder was based on false or misrepresentation of Bidder’s qualification information, - if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for, or in executing, a GoN/DP-financed contract. - if the Successful Bidder fails to sign the Contract. - if the bidder fails to inform or informs after the specified time about the saturation of maximum number of contracts as per ITB 4.11. - a Bidder requests for withdrawal or modification of its bid: (i) after the Bid Submission deadline and during the period of validity specified by the Bidder on the Letter of Technical Bid and Price Bid, in case of electronic submission; (ii) from the period twenty-four hours prior to bid submission deadline up to the period of bid validity specified by the Bidder on the Letter of Technical Bid and Price Bid, in case of hard copy submission. - if the bidder does not provide clarifications of its Bid by the date and time set in the Employer’s request for clarification pursuant to ITB 27. - a Bidder changes the prices or substance of the bid while providing information pursuant to ITB 27. - A bidder declared blacklisted and ineligible by the GoN, Public procurement Monitoring Office (PPMO) and/or the DP in case of DP funded project, shall be ineligible to bid for a contract during the period of time determined by the GoN, PPMO and/or the DP. - The Contractor shall permit the GoN/DP to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by auditors appointed by the GoN/DP, if so required by the GoN/DP. - DP Funded: In pursuance of the fraud and corruption policy, the DP. - will reject a Bid if it determines that the bidder recommended for award has directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question; - will cancel the portion of the loan/ credit/ grant allocated to a contract if it determines at any time that representative(s) of the GoN or of a beneficiary of the fund engaged in corrupt, fraudulent, collusive, or coercive practices during the procurement or the execution of that contract, without the GoN having taken timely and appropriate action satisfactory to the DP to address such practices when they occur. 3.7 A bidder declared blacklisted and ineligible by the GoN, Public Procurement Monitoring Office (PPMO) and/or the DP in case of DP funded project, may be ineligible to bid for a contract during the period of time determined by the GoN, PPMO and/or the DP. 3.8 In case of a natural person or firm/institution/company which is already declared blacklisted and ineligible by the GoN, any other new or existing firm/institution/company owned partially or fully by such Natural person or Owner or Board of director of blacklisted firm/institution/company; shall not be eligible bidder. |
| - Eligible Bidders | - A Bidder may be a natural person, private entity, or government-owned entity—subject to ITB 4.5—or any combination of them in the form of a Joint Venture (JV) under an existing agreement, or with the intent to constitute a legally-enforceable joint venture. In the case of a JV: - all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. Maximum number of JV and other provision for JV shall be as per specified in the BDS. The qualification requirement of the parties to the JV shall be as specified in Section 3; Evaluation and qualification Criteria, and - the JV shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the bidding process and, in the event the JV is awarded the Contract, during Contract execution. - A Bidder, and all parties constituting the Bidder, shall have the nationality of Nepal or any country or eligible countries mentioned in the BDS. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, or incorporated, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed sub-Contractors or suppliers for any part of the Contract including related services. - A Bidder shall not have a conflict of interest. A Bidder found to have a conflict of interest shall be disqualified. A Bidder may be considered to be in a conflict of interest with one or more parties in this bidding process, if: - they have controlling partners in common; or - they receive or have received any direct or indirect subsidy from any of them; or - they have the same legal representative for purposes of this bid; or - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about or influence on the Bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or - a Bidder participates in more than one bid in this bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which the party is involved. However, this does not limit the inclusion of the same sub-Contractor in more than one bid; or - a Bidder or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the Contract that is the subject of the Bid; or - a Bidder or any of its affiliates has been hired (or is proposed to be hired) by the Employer as Engineer for the Contract. - a Bidder that has a close business or family relationship with a professional staff of the Procuring Entity. - A firm that is under a declaration of ineligibility by the GoN/DP in accordance with ITB 3, at the date of the deadline for bid submission or thereafter, shall be disqualified. The list of debarred firms is available at the electronic address specified in the BDS. - Enterprises owned by GoN shall be eligible only if they can establish that they are legally and financially autonomous and operate under commercial law, and that they are not a dependent agency of the GoN. - Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. - In case a prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. - Firms shall be excluded in any of the cases, if - by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Employer’s country prohibits any import of goods or Contracting of works or services from that country or any payments to persons or entities in that country. - DP Funded: as a matter of law or official regulation, Nepal prohibits commercial relations with that country, provided that the DP is satisfied that such exclusion does not preclude effective competition for the supply of goods or related services required; - DP Funded: a firm has been determined to be ineligible by the DP in relation to their guidelines or appropriate provisions on preventing and combating fraud and corruption in projects financed by them. - Domestic Bidder shall be eligible only if the bidder has obtained Permanent Account Number (PAN) and Value Added Tax (VAT) Registration Certificate(s) and Tax Clearance Certificate or proof of submission of income return as stated in BDS from the Inland Revenue Office. Foreign bidder shall be eligible only if the bidder submits the documents indicated in the BDS at the time of bid submission and a declaration to submit the document(s) indicated in the BDS at the time of contract agreement. - Maximum number of running contracts that a Bidder, and all parties constituting the Bidder can have shall be as specified in BDS. The bidders shall be considered ineligible if number of running contracts exceeds the number as specified. - For the purpose of ITB 4.10 above, the bidder shall declare that the bidder, and all parties constituting the Bidder have not already secured maximum number of construction contracts (in open competitive bidding) as specified in BDS. If the bidder, and all parties constituting the Bidder has participated in bidding process of many public entities and during that period the maximum number of contracts have been attained as specified saturates due to issuance of letters of acceptance by a particular public entity, the bidder shall inform in written to all other concerned public entities, where the bidder have participated in bidding process, within three days of issuance of last letter of acceptance that saturates the maximum number of contracts as specified. |
| - Eligible Materials, Equipment and Services | - The materials, equipment and services to be supplied under the Contract shall have their origin in any source countries as defined in ITB 4.2 above and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment and services. ### For purposes of ITB 5.1 above, “origin” means the place where the materials and equipment are mined, grown, produced or manufactured, and from which the services are provided. Materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that differs substantially in its basic characteristics or in purpose or utility from its components. |

| Contents of Bidding Document |  |
| --- | --- |
| - Sections of Bidding Document | - The Bidding Document consist of Parts I, II, and III, which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART I Bidding Procedures Section 1 - Instructions to Bidders (ITB) Section 2 - Bid Data Sheet (BDS) Section 3 - Evaluation and Qualification Criteria (EQC) Section 4 - Bidding Forms (BDF) PART II Requirements Section 5 – Works Requirements (WRQ) Section 6 – Bill of Quantities (BOQ) PART III Conditions of Contract and Contract Forms Section 7 - General Conditions of Contract (GCC) Section 8 - Special Conditions of Contract (SCC) Section 9 - Contract Forms (COF) - The Invitation for Bids issued by the Employer is not part of the Bidding Document. - The Employer is not responsible for the completeness of the Bidding Document and their Addenda, if they were not obtained directly from the source stated by the Employer in the Invitation for Bids. - The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the bid. |
| - Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | - A prospective Bidder requiring any clarification of the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise any question or curiosity during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer shall be required to make available as soon as possible the answer to such question or curiosity in writing to any request for clarification, provided that such request is received as mentioned in BDS. The Employer shall forward copies of its response to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 22.2. - The Bidder is encouraged to visit and examine the Site of Works and its surroundings and obtain for itself, on its own risk and responsibility, all information that may be necessary for preparing the bid and entering into a Contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense. - The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. - The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. - The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer as mentioned in BDS. - Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. - Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| - Amendment of Bidding Document | - At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Document by issuing addenda. - Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. - To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB 22.2. However, the time available to submit bids shall not be less than five (5) days since amendment in bidding document. |
| Preparation of Bids |  |
| - Cost of Bidding | - The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| - Language of Bid | - The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| - Documents Comprising the Bid | - The Bid shall comprise two envelopes submitted simultaneously, one called the Technical Bid containing the documents listed in ITB 11.2 and the other the Price Bid containing the documents listed in ITB 11.3, both envelopes enclosed together in an outer single envelope. - The Technical Bid shall comprise the following: - Letter of Technical Bid; - Completed Schedules, in accordance with ITB 12; - Bid Security, in accordance with ITB 19; - Alternative Technical Bids, at Bidder’s option and if permissible, in accordance with ITB 13; - Written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 20.2; - Documentary evidence in accordance with ITB 17 establishing the Bidder’s qualifications to perform the Contract; - Technical Proposal in accordance with ITB 16; - In the case of a bid submitted by a JV, the JV agreement, or letter of intent to enter into a JV including a draft agreement, indicating at least the parts of the Works to be executed by the respective partners; and - any other required documents, which is not against the provision of Procurement Act/Regulation/Directives and Standard Bidding Document issued by PPMO as specified in the BDS. - The Price Bid shall comprise the following: (a) Letter of Price Bid; (b) completed Bill of Quantities, Price Schedules, in accordance with ITB 12 and ITB 14, or as stipulated in the BDS; (c) alternative price Bids, at Bidder’s option and if permissible, in accordance with ITB 13; (d) Any other document required in the BDS. - The Bidder is solely responsible for the authenticity of the documents submitted by the Bidder. - The Technical Bid shall not include any financial information related to the Price Bid. A Technical Bid containing such material financial information shall be declared non-responsive. |
| - Letter of Bid and Schedules | - The Letter of Technical Bid and Priced Bid, Schedules, and all documents listed under Clause 11, shall be prepared using the relevant forms in Section 4 (Bidding Forms), if so provided. The forms must be completed without any alterations to the text, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested. |
| - Alternative Bids | - Unless otherwise indicated in the BDS, alternative bids shall not be considered. - When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different times for completion. - When specified in the BDS pursuant to ITB 13.1, and subject to ITB 13.4 below, Bidders wishing to offer technical alternatives to the requirements of the Bidding Document must first price the Employer’s design as described in the Bidding Document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. - When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the Works. Such parts will be identified in the BDS and described in Section 5 (Employer’s Requirements). The method for their evaluation will be stipulated in Section 3 (Evaluation and Qualification Criteria). |
| - Bid Prices and Discounts | - The prices and discounts quoted by the Bidder in the Letter of Price Bid and in the Schedules shall conform to the requirements specified below. - The Bidder shall submit a Price bid for the whole of the works described in ITB 1.1 by filling in prices for all items of the Works, as identified in Section 4 (Bidding Forms). In case of Unit Rate Contracts, the Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities. Items against which no rate or price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bill of Quantities. - The price to be quoted in the Letter of Price Bid shall be the total price of the Bid, excluding any discounts offered. - Unconditional discounts, if any, and the methodology for their application shall be quoted in the Letter of Price Bid, in accordance with ITB 12.1. - If so indicated in ITB 1.1 and ITB 36.4, bids are invited for individual Contracts or for any combination of Contracts (packages). Bidders wishing to offer any price reduction for the award of more than one Contract shall specify in their bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package. Price reductions or discounts shall be submitted in accordance with ITB 14.3, provided the bids for all Contracts are submitted and opened at the same time. - Unless otherwise provided in the BDS and the Conditions of Contract, the prices quoted by the Bidder shall be fixed. If the prices quoted by the Bidder are subject to adjustment during the performance of the Contract in accordance with the provisions of the Conditions of Contract, the Bidder shall furnish the indices and weightings for the price adjustment formulae in the Table of Adjustment Data in Section 4 (Bidding Forms) and the Employer may require the Bidder to justify its proposed indices and weightings. - The bidder is subject to local taxes such as VAT, social charges or income taxes on nonresident international personnel, and also duties, fees, levies on amounts payable by the employer under the Contract. All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 30 days prior to the deadline for submission of bids, shall be included in the rates and prices and the total bid price submitted by the Bidder. |
| - Currencies of Bid and Payment | - The unit rates and the prices shall be quoted by the bidder entirely in Nepalese currency if not otherwise specified in the BDS. - Bidders shall indicate the portion of the bid price that corresponds to expenditures incurred in Nepalese currency in the Schedule of Payment Currencies included in Section 4 (Bidding Forms). - Bidders expecting to incur expenditures in other currencies for inputs to the Works supplied from outside the Employer’s country and wishing to be paid accordingly may indicate up to three convertible foreign currencies included in daily publication of Nepal Rastra Bank foreign currency exchange rate in the Schedule of Payment Currencies included in Section 4 (Bidding Forms). - The rates of exchange to be used by the bidder for currency conversion during bid preparation shall be the selling rates for similar transactions prevailing on the date 30 days prior to the deadline for submission of bids published by Nepal Rastra Bank. Bidders should note that for the purpose of payments, the exchange rates confirmed by Nepal Rastra Bank as the selling rates prevailing 30 days prior to the deadline for submission of bids shall apply for the duration of the Contract so that no currency exchange risk is borne by the bidder. - Foreign currency requirements indicated by the bidders in the Schedule of Payment Currencies shall include but not limited to the specific requirements for - expatriate staff and labor employed directly on the Works; - social, insurance, medical and other charges relating to such expatriate staff and labor, and foreign travel expenses; - imported materials, both temporary and permanent, including fuels, oil and lubricants required for the Works; - depreciation and usage of imported Plant and Contractor's Equipment, including spare parts, required for the Works; - foreign insurance and freight charges for imported materials, Plant and Contractor's Equipment, including spare parts; and - overhead expenses, fees, profit, and financial charges arising outside the Employer's country in connection with the Works. - Bidders may be required by the Employer to clarify their foreign currency requirements, and to substantiate that the amounts included in the unit rates and prices and shown in the Schedule of Payment Currencies are reasonable and responsive to ITB 15.3 above, in which case a detailed breakdown of its foreign currency requirements shall be provided by the Bidder. - Bidders should note that during the progress of the Works, the foreign currency requirements of the outstanding balance of the Contract Price may be adjusted by agreement between the Employer and the Contractor in order to reflect any changes in foreign currency requirements for the Contract, in accordance with Sub-Clause 14.15 of the Conditions of Contract. Any such adjustment shall be effected by comparing the percentages quoted in the bid with the amounts already used in the Works and the Contractor's future needs for imported items. |
| - Documents Comprising the Technical Proposal | - The Bidder shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule and any other information as stipulated in Section 4 (Bidding Forms), in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. |
| - Documents Establishing the Qualifications of the Bidder | - To establish its qualifications to perform the Contract in accordance with Section 3 (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding information sheets included in Section 4 (Bidding Forms). - Domestic Bidders, individually or in joint ventures, applying for eligibility for domestic preference shall supply all information required to satisfy the criteria for eligibility as described in ITB 34 if margin of preference for domestic bidders is applicable in accordance with ITB 34. |
| - Period of Validity of Bids | - Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. If the prescribed bid submission deadline date falls on a government holiday, then the next working day shall be considered as the bid submission deadline date. In such case the validity period of the bids shall be considered from the original bid submission deadline date. A bid valid for a shorter period shall be rejected by the Employer as non-responsive. In the case of electronic bid submission, if any technical issue arises in the handling of the e-GP system, the PPMO may extend the deadline for bid submission. However, the validity period of the bids shall still be counted from the original bid submission deadline. - In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 19, it shall also be extended 30 days beyond the deadline of the period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its Bid and to include any additional conditions against the provisions specified in Bid Documents. |
| - Bid Security | - The Bidder shall furnish as part of its bid, in original form, a bid security as specified in the BDS. In case of e-submission of bid, the Bidder shall upload scanned copy of Bid security letter at the time of electronic submission of the bid. The Bidder accepts that the scanned copy of the Bid security shall, for all purposes, be equal to the original. The details of original Bid Security and the scanned copy submitted with e-bid should be the same otherwise the bid shall be non-responsive. - The bid security shall be, at the Bidder’s option, in any of the following forms: (a) an unconditional bank guarantee from Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law or; (b) a cash deposit voucher in the Employer's Account as specified in BDS. In the case of a bank guarantee, the bid security shall be submitted either using the Bid Security Form included in Section IV (Bidding Forms) or in another Form acceptable to the employer. The form must include the complete name of the Bidder. The bid security shall be valid for minimum thirty (30) days beyond the original validity period of the bid, or beyond any period of extension if requested under ITB 18.2. A bid security valid for a shorter period shall be rejected by the Employer as non-responsive. - The bid security issued by any foreign Bank outside Nepal must be counter guaranteed by a Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law in Nepal. - Any bid not accompanied by an enforceable and substantially compliant bid security, if required in accordance with ITB 19.1, shall be rejected by the Employer as nonresponsive. In case of e- Submission, if the scanned copy of an acceptable Bid Security letter is not uploaded with the electronic Bid then Bid shall be rejected. - The bid security of unsuccessful Bidders shall be returned within three days, once the successful bidder has furnished the required performance security and signed the Contract Agreement pursuant to ITB 41.1 and ITB 42.1. - The bid security shall be forfeited if: (a) a Bidder requests for withdrawal or modification of its bid, except as provided in ITB 18.2: (i) during the period of bid validity specified by the Bidder on the Letter of Technical Bid and Price Bid, in case of electronic submission; (ii) from the period twenty-four hours prior to bid submission deadline up to the period of bid validity specified by the Bidder on the Letter of Technical Bid and Price Bid, in case of hard copy submission. (b) a Bidder changes the prices or substance of the bid while providing information pursuant to clause 27.1; (c) a Bidder involves in fraud and corruption pursuant to clause 3.1; (d) the successful Bidder fails to: (i) furnish a performance security in accordance with ITB 41.1; (ii) sign the Contract in accordance with ITB 42.1; or (iii) accept the correction of arithmetical errors pursuant to clause 32 ; (e) if the bidder fails to inform about the saturation of the maximum number of contracts as per ITB 4.11 (for GoN funded only) - The Bid Security of a JV shall be in the name of the JV that submits the bid. If the JV has not been legally constituted at the time of bidding, the Bid Security shall be in the names of all future partners as named in the letter of intent mentioned in ITB 4.1. |
| - Format and Signing of Bid | - The Bidder shall prepare one original of the documents comprising the bid as described in ITB 11 and clearly mark it “ORIGINAL”. Alternative bids, if permitted in accordance with ITB 13, shall be clearly marked “ALTERNATIVE”. In addition, the Bidder shall submit copies of the bid in the number specified in the BDS, and clearly mark each of them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. In case of e-submission of bid, the Bidder shall submit his bid electronically in PDF or web forms files as specified in ITB Clause 21.1(b), If a Bidder submits both the electronic bid and a bid in hard copy within the bid submission deadline, then the submitted Bids shall be accepted for evaluation provided that the facts and figures in hard copy confirm to those in electronic bid. If there is any major discrepancy in fact and figures in the electronic bid and bid in hard copy, it shall be treated as two separate bids from one Bidder and both the Bids shall be disqualified, as per ITB Clause 4.3 (e). - The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the bid, except for unamended printed literature, shall be signed or initialed by the person signing the bid. - Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the bid. |

| Submission and Opening of Bids |  |
| --- | --- |
| - Sealing and Marking of Bids | - Bidders may always submit their bids by mail or by hand or by courier. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Procedures for submission, sealing and marking are as follows: (a) Bidders submitting bids by mail, by hand or by courier i. Bidders shall enclose the original of the Technical Bid, and the original of the Price Bid and each copy of the Technical Bid and Price Bid, including alternative bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as : “ORIGINAL TECHNICAL BID”,“ORIGINAL PRICE BID”, “ALTERNATIVE BID” and “COPY OF TECHNICAL BID” and “COPY OF PRICE BID”. These envelopes containing the original and the copies shall then be enclosed in one single envelope. ii. The inner and outer envelopes shall: (aa) bear the name and address of the Bidder; (bb) be addressed to the Employer as provided in BDS 22.1; (cc) bear the specific identification of this bidding process indicated in BDS 1.1; (dd) The outer envelope and the inner envelope containing Technical Bid shall bear a warning not to open before the time and date for the opening of Technical Bid in accordance with ITB 25.1. iii. The inner envelope containing the Price Bid shall bear a warning not to open until advised by the Employer in accordance with ITB 25.7 iv. If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid. (b) Electronic Bid Submission Procedures : Bidders submitting Bids electronically shall follow the electronic bid submission procedure specified in this clause as follows: - For e-submission, the bidder is required to register in the e-GP portal https://www.bolpatra.gov.np. for downloading and submitting the bid electronically. - Bidders registered in the e-GP portal of PPMO may download the bidding document from http://www.bolpatra.gov.np after login at no cost. - The bidder shall then prepare/fill the documents and forms included in the issued bid documents or the downloaded bid documents from the e-GP portal of PPMO - http://www.bolpatra.gov.np. as applicable. The required documents and forms shall be prepared in PDF form and/or shall be filled in the web forms in the e-GP system as specified below: - Technical Bid: - S. N.; - Document; - Requirement; - Remarks. - 1; - Letter of Technical Bid; - Mandatory; - PDF/Web Forms. - 2; - Bid Security (Bank Guarantee); Mandatory; PDF. - 3; - Company/Firm Registration Certificate; Mandatory; PDF. - 4; - VAT registration Certificate; Mandatory (for domestic bidders and resident foreign bidders only); PDF. - 5; - Tax Clearance Certificate/Tax return submission evidence/evidence of time extension; Mandatory (for domestic bidders and resident foreign bidders only); PDF. - 6; - Power of Attorney of Bid signatory; Mandatory; PDF. - 7; - Business Registration (Licence) Certificate; Mandatory, if Applicable; PDF. - 8; - Joint venture agreement; Mandatory in case of JV Bids Only; PDF. - 9; - Qualification Information; Mandatory; Web Forms (Experience, Turnover, etc.). - 10; - Additional Document, if any; Mandatory; PDF. Price Bid; - S. N.; - Document; - Requirement; - Remarks. - 1; - Letter of Price Bid; - Mandatory; - PDF/Web Forms. - 2; - Applicable Price Adjustment Table; Mandatory If applicable; Web Forms. - 3; - Completed BOQ or Price Schedule; Mandatory; Web Forms. Note: - The documents specified as “Mandatory” should be included in e-submission and non-submission of the documents shall be considered as non-responsive bid. - Bidders (all partners in case of JV) should verify/update their profile documents as appropriate for the specific bid before submitting their bid electronically. - The Bidder shall then upload the PDF bid files and submit the complete bid online through e-GP portal of PPMO- http://www.bolpatra.gov.np within the specified date and time. - Bidders are advised to download the bid submission report to ensure that all the documents/ files are up to date and complete. - The Bidder / Bid shall meet the following requirements and conditions for e-submission of bids; - The e-submitted bids must be readable through open standards interfaces. Unreadable and or partially submitted bid files shall be considered incomplete and rejected for further bid evaluation. - In addition to electronically submitted PDF files/web forms, the Bidder shall be required to submit original bid security letter/ documents and clarifications as specified in ITB Clause 27. If a bidder does not submit the original Bid security letter and requested documents and or clarifications within the specified time limit then the bid shall not be considered for further evaluation. - If major discrepancy is found between the electronically submitted PDF bid files and the documents/ clarifications provided by the Bidder as per ITB Clause 27, then the bid shall not be considered for further evaluation. - The facility for submission of bid electronically through e-submission is to promote transparency, non-discrimination, equality of access, and open competition in the bidding process. The Bidders are fully responsible to use the e-submission facility properly in e-GP portal of PPMO- http://www.bolpatra.gov.np as per specified procedures and in no case the Employer shall be held liable for Bidder's inability to use this facility. - When a bidder submits electronic bid through the PPMO e-GP portal, it is assumed that the bidder has prepared the bid by studying and examining the complete set of the Bidding documents including specifications, drawings and conditions of contract. - Bidders who submit electronic bid should deposit the bidding document fee as specified in IFB and upload the scan copy (in pdf format) of the deposit voucher at the time of bid submission. The deposited amount shall be verified by the Employer during the bid evaluation process. The submitted Bid shall be non-responsive and shall not be evaluated if the cost for bidding document is not deposited as specified in the IFB. |
| - Deadline for Submission of Bids | - Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. In case of e-submission, the standard time for e-submission is Nepal Standard Time as set out in the server. The e-procurement system will accept the e-submission of bid from the date of publishing of notice and will automatically not allow the e-submission of bid after the deadline for submission of bid. - The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| - Late Bids | - The Employer shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB 22. Any bid received by the Employer after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the Bidder. |
| - Withdrawal, and Modification of Bids | - A Bidder may withdraw, or modify its bid after it has been submitted either in hard copy or by e-submission. Procedures for withdrawal or modification of submitted bids are as follows: - Bids submitted in hard Copy a) Bidders may withdraw or modify its bids by sending a written notice in a sealed envelope, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 20.2 before 24 hours prior to the deadline of submission of bids. The corresponding modification of the bid must accompany the respective written notice. All notices must be: (aa) prepared and submitted in accordance with ITB 20 and ITB 21,and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL”, “MODIFICATION;” and (bb) received by the Employer twenty four hour prior to the deadline prescribed for submission of bids, in accordance with ITB 22. (cc) The bidder shall clearly specify on envelope whether “MODIFICATION”’ is of Technical Bid or Price Bid. - E-submitted bids. - Bidder may submit modification or withdrawal prior to the deadline prescribed for submission of bid through e-GP system by using the forms and instructions provided by the system. Once a Bid is withdrawn, bidder will not be able to submit another bid response for the same bid. - Bids requested to be withdrawn in accordance with ITB 24.1 shall be returned unopened to the Bidders after completion of the bid opening. - Bidder may submit request for withdrawal or modification only one time. - No bid may be withdrawn if the bid has already been modified. - Except in case of any modification or correction in bid document made by procuring entity, Bidder may submit request for withdrawal or modification only one time. - In case of hard copy bid, no bid may be withdrawn if the bid has already been modified; except in case of any modification or correction in bid document by procuring entity. - Request for withdrawal or modification must be made through the same medium of submission. Request for withdrawal or modifications through different medium shall not be considered. - The following provisions apply for withdrawal or modification of the Bids: (i) In case of bids submitted in hard copy no bid shall be withdrawn or modified in the interval between 24 hours prior to the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. (ii) In case of e-submitted bids no bids shall be withdrawn or modified in the interval between deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |
| - Bid Opening | - The Employer shall open the bids in public at the address, date and time specified in the BDS in the presence of Bidders` designated representatives and anyone who choose to attend. Then the Employer shall segregate the Technical Bid and Price Bid separately. The Price Bids will remain unopened and will be held in custody of the Employer until the specified time of their opening. If the Technical Bid and Price Bid are submitted together in one inner envelope, the Employer may reject the entire Bid. - The Employer shall download the e-submitted Bid files. The e-procurement system allows the Employer to download the e-submitted bid files (report) only after bid opening date and time after login simultaneously by at least two members of the Bid opening commitee. - After downloading each e-bid, electronically submitted Technical Bid shall be opened at first in the same time and date as specified above. Electronic Bids shall be opened one by one and read out. The e-submitted technical bids must be readable through open standards interfaces. Unreadable and or partially submitted bid files shall be considered incomplete. - Thereafter, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding Bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “MODIFICATION” shall be opened and read out with the corresponding bid. No Technical Bid and/or Price Bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out and recorded at bid opening. Only the Technical Bid, both Original as well as Modification, are to be opened, read out, and recorded at the opening. Price Bids, both Original and Modification, will remain unopened in accordance with ITB 25.1. - All other envelopes holding the Technical Bid shall be opened one at a time, reading out: the name of the Bidder; whether there is a modification; the presence of a bid security and any other details as the Employer may consider appropriate. Only Technical Bids read out and recorded at bid opening shall be considered for evaluation. No bid shall be rejected at opening of Technical Bids except for late bids, in accordance with ITB 23.1. - The Employer shall prepare a record of the opening of Technical Bids that shall include, as a minimum: the name of the Bidder and whether there is a withdrawal, or modification; and the presence or absence of a bid security. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. - At the end of the evaluation of the Technical Bids, the Employer will invite bidders who have submitted substantially responsive Technical Bids and who have been determined as being qualified for award to attend the opening of the Price Bids. The date, time, and location of the opening of Price Bids will be advised in writing by the Employer. Bidders shall be given at least 15 days' notice for the opening of Price Bids. - The Employer will notify Bidders in writing who have been rejected on the grounds of their Technical Bids being substantially nonresponsive to the requirements of the Bidding Document and return their Price Bids unopened. - The Employer shall conduct the opening of Price Bids of all Bidders who submitted substantially responsive Technical Bids, in the presence of Bidders` representatives who choose to attend at the address, on the date, and time specified by the Employer. The Bidder’s representatives who are present shall be requested to sign a register evidencing their attendance. - All envelopes containing Price Bids shall be opened one at a time and the following read out and recorded: - the name of the Bidder; - whether there is a modification; - the Bid Prices, including any discounts and alternative offers; and - any other details as the Employer may consider appropriate. Only Price Bids, discounts, modifications, and alternative offers read out and recorded during the opening of Price Bids shall be considered for evaluation No Bid shall be rejected at the opening of Price Bids. - The Employer shall prepare a record of the opening of Price Bids that shall include, as a minimum, the name of the Bidder, the Bid Price (per lot if applicable), any discounts, modifications and alternative offers. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. |

| Evaluation and Comparison of Bids |  |  |  |
| --- | --- | --- | --- |
| - Confidentiality |  | - Information relating to the examination, evaluation, comparison, and post qualification of bids and recommendation of Contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders. - Any attempt by a Bidder to influence the Employer in the evaluation of the bids or Contract award decisions may result in the rejection of its bid. - Notwithstanding ITB 26.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it may do so in writing. |  |
| - Clarification of Bids |  | - To assist in the examination, evaluation, and comparison of the Technical and Price Bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the substance of the Technical Bid or prices in the Price Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Price Bids. In case of e-submission of bid, upon notification from the employer, the bidder shall also submit the original of documents comprising the Technical and Price Bid as per ITB 11 for verification of submitted documents for acceptance of the e-submitted bid. - If a Bidder does not provide clarifications of its bid by the date and time set in the Employer’s request for clarification, its bid shall be rejected. |  |
| - Deviations, Reservations, and Omissions |  | - During the evaluation of bids, the following definitions apply: - “Deviation” is a departure from the requirements specified in the Bidding Document; - “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and - “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |  |
| - Determination of Responsiveness |  | - The Employer’s determination of a bid’s responsiveness is to be based on the contents of the bid itself, as defined in ITB11. - A substantially responsive Technical Bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - if accepted, would: (i) affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or (ii) limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive bids. - The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 16, Technical Proposal, in particular, to confirm that all requirements of Section 5 (Works Requirements) have been met without any material deviation, reservation or omission. - If a bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. - In case of e-submission bids, the Employer evaluates the bid on the basis of the information in the electronically submitted bid files. If the Bidder cannot substantiate or provide evidence to establish the information provided in e-submitted bid through documents/clarifications as per ITB Clause 27, the bid shall not be considered for further evaluation. - Except in case of e-submission, the Financial Bid of the bidder, which is evaluated as substantially non-responsive in technical bid, shall be returned to the respective bidders. |  |
| - Nonconformities, Errors, and Omissions - Qualification of the Bidder |  | 30.1 Provided that a bid is substantially responsive, the Employer may waive any nonconformities in the bid that do not constitute a material deviation, reservation or omission. 30.2 Provided that a Technical Bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Technical Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the Price Bid. Failure of the Bidder to comply with the request may result in the rejection of its bid. 30.3 Provided that a Technical bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. The adjustment shall be made using the methods indicated in Section 3 (Evaluation and Qualification Criteria). 30.4 If minor discrepancies are found such as in technical specification, description, feature which do not make the bid to be rejected, then the cost, which is calculated to the extent possible due to such differences shall be included while evaluating the bid. 30.5 If the value of such non-conformities is found to be more than fifteen percent of the quoted amount of the bidder on account of minor discrepancies pursuant to ITB 30.4, such bid shall be considered ineffective in substance and shall not be involved in evaluation. 31.1 The Employer shall determine to its satisfaction during the evaluation of Technical Bids whether Bidders meet the qualifying criteria specified in Section 3 (Evaluation and Qualification Criteria). 31.2 The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 17. 31.3 An affirmative determination of qualification shall be a prerequisite for the opening and evaluation of a Bidder’s Price Bid. A negative determination shall result into the disqualification of the Bid, in which event the Employer shall return the unopened Price Bid to the Bidder. |  |
| - Correction of Arithmetical Errors |  | - During the evaluation of Price Bids, the Employer shall correct arithmetical errors on the following basis: - only for unit price Contracts, if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected; - if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and - if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. - If a Bidder does not accept the correction of errors, its bid shall be disqualified and its bid security shall be forfeited. |  |
| - Conversion to Single Currency | - For evaluation and comparison purposes, the currency (ies) of the bid shall be converted into a single currency as specified in the BDS. |  |
| - Domestic Preference | - Unless otherwise specified in the BDS, a domestic preference shall be a factor in bid evaluation |  |
| - Subcontractors - Evaluation of Price Bids |  | 35.1 The Employer may permit subcontracting for certain specialized works as indicated in Section 3. When subcontracting is permitted by the Employer, the specialized sub-contractor’s experience shall be considered for evaluation. Section 3 describes the qualification criteria for sub-contractors. Bidders may propose subcontracting up to the percentage of total value of contracts or the volume of works as specified in the BDS. - The Employer shall evaluate Price Bid of each bid for which the Technical Bid has been determined to be substantially responsive. The Employer shall use the criteria and methodologies listed in this Clause. No other evaluation criteria or methodologies shall be permitted. - To evaluate a Price bid, the Employer shall consider the following: - the bid price, excluding Value Added Tax, Provisional Sums, and the provision, if any, for contingencies in the Summary Bill of Quantities, for Unit Rate Contracts, or Schedule of Prices for lump sum Contracts, but including Day work items, where priced competitively; - adjustment for correction of arithmetic errors in accordance with ITB 32; - adjustment due to discounts offered in accordance with ITB 14.4; - converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 33; - adjustment for nonconformities in accordance with ITB 30.3; - application of all the evaluation factors indicated in Section 3 (Evaluation and Qualification Criteria); If the evaluated Bid Price of the Bidder is more than 30 (thirty) percent below or substantially higher than the cost estimate, the Employer shall reject the Bid as non-responsive. - The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. - If this Bidding Document allows Bidders to quote separate prices for different lots Contracts, and to award multiple Contracts to a single Bidder as specified in BDS, the methodology to determine the lowest evaluated price of the Contract combinations, including any discounts offered in the Letter of Bid, is specified in Section 3 (Evaluation and Qualification Criteria). - If the bid for a Unit Rate Contract, evaluated as per ITB 37, is front-loaded or has quoted abnormally high rate for any item believing that the item was underestimated, the Employer shall require the Bidder to provide clarification along with detailed rate analysis, for any or all items of the Bill of Quantities. The rate analysis submitted shall be analyzed and compared against prevailing norms and rates, on the basis of the work execution methodology, technology, and management methods specified by the bidder. If the clarification is deemed unsatisfactory, the Employer shall require that the amount of the performance security be increased at the expense of the Bidder as specified in BDS. - In case of e-submission bids, the Employer evaluates the bid on the basis of the information in the electronically submitted bid files. If the Bidder cannot substantiate or provide evidence to establish the information provided in e-submitted bid through documents/clarifications as per ITB Clause 27, the bid shall not be considered for further evaluation. - Notwithstanding ITB 36.2, if all the bids evaluated are substantially higher than the cost estimate, the employer may negotiate with the bidder who submitted the lowest evaluated substantially responsive Bid to propose a lump sum discount rate in order to bring the bid price within the approved cost estimate. However, no change in the substance of the bid is permitted during the negotiations. - If no agreement can be reached as per ITB 36.7, the employer shall cancel the procurement proceedings. |  |
| - Comparison of Bids |  | - The Employer shall compare all substantially responsive bids in accordance with ITB 36. The Employer shall determine the Average Bid Price of all the substantially responsive Bids. The Bid Price which is closest to the Average Bid Price AND is not substantially higher than the cost estimate shall be selected for awarding the contract. In case two or more Bid Prices are determined to be equally closest to the Average Bid Price, the Bid Price which is below the Average Bid Price shall be selected for awarding the contract. - While evaluating the Bid Price as per ITB 37.1, if the Bid Price of two or more Bidders is found to be equal, the Employer shall select the bid for awarding the contract by drawing of lots in presence of Bidders’ designated representatives who choose to attend in date, time and place as notified by the Employer in writing to the concerned bidders. The Bidders’ representatives who are present shall be requested to sign a record evidencing their attendance. The omission of a Bidder’s signature on the record or the absence of a Bidder during the drawing of lots shall not invalidate the contents and the effect of the record. The method of drawing of lots shall be determined by the Employer. |  |
| - Employer’s Right to Accept Any Bid, and to Reject Any or All Bids |  | - The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to Contract award, without thereby incurring any liability to Bidders. In case of annulment, all bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |  |
| Award of Contract |  |  |  |
| - Award Criteria |  | - The Employer shall award the Contract to the Bidder whose bid price is selected as per ITB 36 and ITB 37 and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be qualified to perform the Contract satisfactorily. |  |
| - Letter of Intent to Award the Contract/ Notification of Award |  | - The Employer shall notify the concerned Bidder whose bid has been selected in accordance with ITB 39.1 within seven days of the selection of the bid, in writing that the Employer has intention to accept its bid and the information regarding the name, address and amount of selected bidder shall be given to all other bidders who submitted the bid. - After issuance of the notice under ITB 40.1 if the concerned bidder provides information pursuant to ITB 4.11 regarding saturation of maximum number of contracts, the employer shall disqualify the bidder and shall select the next Bidder whose Bid Price is closest to the previously determined Average Bid Price in accordance with ITB 39.1 and notify accordingly as per ITB 40.1. - If no bidder submits an application within a period of seven days of the notice provided under ITB 40.1, the Employer shall, accept the bid selected in accordance with ITB 39.1 and Letter of Acceptance shall be communicated to the selected bidder prior to the expiration of period of Bid validity, to furnish the performance security and sign the contract within fifteen days. - After communicating letter of acceptance under ITB 40.3, if the concerned bidder provides information pursuant to ITB 4.11 regarding saturation of maximum number of contracts, the employer shall reject the bid of that bidder and shall select the next Bidder whose Bid Price is closest to the previously determined Average Bid Pricein accordance with ITB 39.1 and shall issue the notice accordingly as per ITB 40.1. In such case bid security of the rejected bidder shall not be forfeited. - At the same time, the Employer shall affix a public notice on the result of the award on its notice board and may make arrangements to post the notice into its website, if it has; and if it does not have, into the website of the Public Procurement Monitoring Office, identifying the bid and lot numbers and the following information: (i) name of each Bidder who submitted a Bid; (ii) bid prices as read out at Bid Opening; (iii) name and evaluated prices of each Bid; (iv) name of bidders whose bids were rejected and the reasons for their rejection; and (v) name of the winning Bidder, and the Price it offered, as well as the duration and summary scope of the Contract awarded. |  |
| - Performance Security |  | - Within Fifteen (15) days of the receipt of Letter of Acceptance from the Employer, the successful Bidder shall furnish the performance security in accordance with the Conditions of Contract, in an amount equal to 5 (five) percent of the Bid Price (without VAT but including PS) from Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law in Nepal using Sample Form for the Performance Security included in Section 9 (Contract Forms), or another form acceptable to the Employer. The performance security issued by any foreign Bank outside Nepal must be counter guaranteed by Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law in Nepal. - Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security. In that event the Employer may award the Contract to the next Bidder whose Bid Price is closest to the previously determined Average Bid Price whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. In such case, the award process shall be repeated according to ITB 40. |  |
| - Signing of Contract |  | - The Employer and the successful Bidder shall sign the Contract Agreement within the period as stated ITB 41.1. - Within thirty (30) days from the date of issuance of notification pursuant to ITB 40.1 unsuccessful bidders may request in writing to the Employer for a debriefing seeking explanations on the grounds on which their bids were not selected. The Employer shall promptly respond in writing to any unsuccessful Bidder who, requests for debriefing. - If the bidder whose bid has been accepted fails to sign the contract as stated ITB 42.1, the Public Procurement Monitoring Office shall blacklist the bidder on recommendation of the Public Entity. |  |
| - Complain and Review |  | - If a Bidder is dissatisfied with the Procurement proceedings or the decision made by the Employer in the intention to award the Contract, it may file an application to the Chief of the Public Entity (Employer) within Seven (7) days of providing the notice under ITB 40.1 by the Public Entity, for review of the proceedings stating the factual and legal grounds. - Late application filed after the deadline pursuant to ITB 43.1 shall not be processed. - The chief of Public Entity (Employer) shall, within five (5) days after receiving the application, give its decision with reasons, in writing pursuant to ITB 43.1: - whether to suspend the procurement proceeding and indicate the procedure to be adopted for further proceedings; or - to reject the application. The decision of the chief of Public Entity shall be final for the Bid amount less than Rupees Twenty Million (NPR. 20,000,000). - If the Bidder is not satisfied with the decision given in accordance with ITB 43.3, or the decision is not given within five (5) days of receipt of application pursuant to ITB 43.1, it can, within seven (7) days of receipt of such decision, file an application to the Review Committee of the GoN, stating the reason of its disagreement on the decision and furnishing the relevant supporting documents. The application may be sent by hand, by post, by courier, or by electronic media at the risk of the Bidder itself. - Late application filed after the deadline pursuant to ITB 43.4 shall not be processed - Within three (3) days of the receipt of application from the Bidder, pursuant to ITB 43.4, the Review Committee shall notify the concerning Public Entity to furnish its procurement proceedings, pursuant to ITB 43.3. - Within three (3) days of receipt of the notification pursuant to ITB 43.6, the Public Entity shall furnish the copy of the related documents to the Review Committee. - The Review Committee, after inquiring from the Bidder and the Public Entity, if needed, shall give its decision within one (1) month of the receipt of the application filed by the Bidder, pursuant to ITB 43.4. - The Bidder, filing application pursuant to ITB 43.4, shall have to furnish a cash amount or Bank guarantee from Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law equivalent to ten percent (10 %) of amount of bid security in case of complaint against decision pursuant to ITB 25.8 and one percent (1%) of its quoted amount in case of complaint against decision pursuant to ITB 40.1 with the validity period of at least ninety (90) days from the date of the filing of application pursuant to ITB 43.4. - If the claim made by the Bidder pursuant to ITB 43.4 is justified, the Review Committee shall return the security deposit pursuant to ITB 43 to the applicant, within seven (7) days of such decision made. - If the Employer does not implement the decision of the Public Procurement Review Committee, the bidder may file an application to the Public Procurement Review Committee. |  |

Section 2 - Bid Data Sheet

This section consists of provisions that are specific to each procurement and supplement the information or requirements included in Section I. Instructions to Bidders.

A.  General

| ITB 1.1 | The number of the Invitation for Bids is : ______________________________ |
| --- | --- |
| ITB 1.1 | The Employer is: ___________________________________________________ |
| ITB 1.1 | The name of the ICB is: ______________________________ The identification number of the ICB is: _________________ The number and identification of lots comprising this ICB is: _______ |
| ITB 2.1 | The name of the Project is: ________________________________________ The Development Partner(DP) is: [insert name if applicable or otherwise insert” Not Applicable] The implementing agency is: _______________________________________ |
| ITB 4.1 (a) | For GoN Funded: Maximum number of partner in a joint venture shall be : 3 (three) In case of Foreign Bidder, Joint Venture with Nepalese Bidder is …………[Insert “Mandatory” or ”Not mandatory”] (For works having estimated amount up to NPR. 10 (Ten) Billion specify “Mandatory”) For DP Funded: [select one options as per DPs Policy] There is no limit on the number of members in a JV or Maximum number of partner in a joint venture shall be : [insert number] |
| ITB 4.2 | Eligible countries [insert if GoN funded – all countries, For DP funded as per their list of eligible country] (Specify the list of eligible countries in a separate section) |
| ITB 4.4 | A list of debarred firms is available at http:/www.ppmo.gov.np [insert other website, if any] |
| ITB 4.9 | Tax Clearance Certificate or Proof of submission of income return for: [insert the applicable fiscal year] The foreign bidder shall declare to submit the following documents at the time of contact agreement [indicate required documents] But, Resident foreign bidder shall submit PAN/VAT certificate and tax clearance certificate or proof of submission of Income Return for [insert the applicable fiscal year] |
| ITB 4.10 & 4.11 | For GoN Funded: Maximum number of running contracts that a Bidder, and all parties constituting the Bidder can have shall be : 5 (Five) [except for bidders participating as JV with maximum share 25 % and not having singed more than two (2) contracts for works of similar nature since 2078-12-03 i.e. March 17, 2022 in Nepal] For DP Funded: [select one options as per DPs Policy] There is no limit on number of running contracts that a Bidder, and all parties constituting the Bidder can have or Maximum number of running contracts that a Bidder, and all parties constituting the Bidder can have shall be : [insert number] |

B.  Bidding Document

| ITB 7.1 | For clarification purposes only, the Employer’s address is: Attention: ______________________________ Street Address: _________________________ Floor/Room number: _____________________ Country: ______________________________ Telephone: : __________________________ Facsimile number: ______________________ Electronic mail address: __________________ |
| --- | --- |
| ITB 7.4 | A Pre-Bid meeting [insert “shall” or “shall not”] take place. If a Pre-Bid meeting will take place, it will be at the following date, time and place: Date: ____________ Time: ____________ Place: ____________ |
| ITB 7.5 | Time for request: Requests for clarification should be received by the Employer no later than 15 days prior to the deadline for submission of bids. |

C.  Preparation of Bids

| ITB 10.1 | The language of the bid is: ______(English)____ |
| --- | --- |
| ITB 11.2 (i) | The Bidder shall submit with its bid the following additional documents: [insert if any additional documents required] |
| ITB 11.3 (b) | In accordance with ITB 12 and ITB 14, the following schedules shall be submitted with the bid, including the priced Bill of Quantities for Unit Rate Contracts and Schedule of Prices for lump sum contracts: _______ |
| ITB 11.3 (d) | The Bidder shall submit with its bid the following additional documents: - Table of Price Adjustment Data as per GCC 13.8 - [insert if any additional documents required] |
| ITB 13.1 | Alternative bids [insert “shall be” or “shall not be”] permitted. |
| ITB 13.2 | Alternative times for completion [insert “shall be” or “shall not be”] permitted. If alternative times for completion are permitted, the evaluation method will be as specified in Section 3 (Evaluation and Qualification Criteria). |
| ITB 13.4 | Alternative technical solutions shall be permitted for the following parts of the Works: [insert detail if applicable otherwise insert “Not Applicable”] If alternative technical solutions are permitted, the evaluation method will be as specified in Section 3 (Evaluation and Qualification Criteria). |
| ITB 14.6 | The prices quoted by the Bidder…. [Insert “shall be” or “shall not be”] subject to adjustment. |
| ITB 15.1 | If the currency of the Bid and payment is other than Nepalese currency : The currency applicable shall be [Insert the name of Currency] The maximum ratio of Nepalese Currency to Foreign Currency with respect to the evaluated bid price shall not be more than …..[Insert the proper ratio, example 70:30 or 80:20 etc…] |
| ITB 18.1 | The bid validity period shall be: One Hundred Twenty (120) days]. |
| ITB 19.1 | The Bidder shall furnish a bid security, from Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law with a minimum of [insert amount (2 to 3 % of estimated amount exclusive of VAT)], which shall be valid for 30 days beyond the validity period of the bid. |
| ITB 19.2 (b) | Account Name: Bank Name: Bank Address: Account Number: |
| ITB 20.1 | In addition to the original of the bid, the number of copies is: [insert the number of copies]. |
| ITB 20.2 | The written confirmation of authorization to sign on behalf of the Bidder shall indicate: [insert” a) The name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid such as a Power of Attorney; and (b) In the case of Bids submitted by an existing or intended JV, an undertaking signed by all parties (i) stating that all parties shall be jointly and severally liable, and (ii) nominating a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the bidding process and, in the event the JV is awarded the Contract, during contract execution. |

D.  Submission and Opening of Bids

| ITB 21.1 | Bidders [insert “shall” or “shall not”] have the option of submitting their bids electronically. |
| --- | --- |
| ITB 22.1 | For bid submission purposes only, the Employer’s address is: Attention: ___________________________________ Street Address: ______________________________ Floor/Room number: __________________________ City: _______________________________________ Country: ____________________________________ The deadline for bid submission is: _______________ Date: ________________ Time: ________________ |
| ITB 25.1 | The bid opening shall take place at: Street Address: ___________________________ Floor/Room number: _______________________ City: ____________________________________ Country: ________________________________ Date: __________________ Time: ___________________ [Insert date and time that is immediately after the Bid Submission deadline] |

E.  Evaluation and Comparison of Bids

| ITB 33.1 | The currency that shall be used for bid evaluation and comparison purposes to convert all bid prices if permitted and expressed in various currencies into a single currency is: The source of exchange rate shall be: Nepal Rastra Bank The date for the exchange rate shall be: 30 days prior to the deadline for submission of bids. |
| --- | --- |
| ITB 34.1 | Domestic preference shall apply and the application methodology shall be as stipulated in Section 3 (Evaluation and Qualification Criteria). |
| ITB 35.1 | Contractor’s proposed subcontracting: Maximum percentage of subcontracting permitted is: 25% of the total contract amount |
| ITB 36.4 | Bidders are [insert “permitted” or “not permitted"] to quote separate prices for lots (Contracts), and a single Bidder will be awarded multiple lots (Contracts) based on provision of Paragraph 1.2, Multiple Contracts Section III (Evaluation and Qualification Criteria): [If permitted to quote separate prices for lots (Contracts), insert the following otherwise delete] Multiple contracts comprising of following lots (contracts): ………………………………. [Insert the name and contract number of the lots (contracts)]………………………. |
| ITB 36.5 | The amount of the performance security be increased by Eight (8) percent of the quoted bid price. |

Section 3 - Evaluation and Qualification Criteria

This Section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders if the bidding was preceded by post-qualification exercise. GoN requires bidders to be qualified by meeting predefined, precise minimum requirements. The method sets pass-fail criteria, which, if not met by the bidder, results in disqualification. In accordance with ITB 32 and ITB 36, no other methods, criteria and factors shall be used. The Bidder shall provide all the information requested in the forms included in Section 4 (Bidding Forms).

## Table of Criteria

1. Evaluation	39

1.1	Adequacy of Technical Proposal	39

1.2	Multiple Contracts	39

1.3   	In Case, other than Multiple Contracts	40

1.4	Completion Time	40

1.5	Alternative Technical Solutions	40

1.6  	Domestic Preference	40

1.7	Quantifiable Nonconformities, Errors and Omissions	40

2.	Qualification	42

2.1	Eligibility	42

2.1.1	Conflict of Interest	42

2.1.2	Government-owned Entity	42

2.1.3   Development Partner Eligibility [if applicable other mention “Not Applicable”]	42

2.1.4	UN Eligibility	42

2.1.5	Bidder’s Running Contracts	43

2.1. 6	VAT and PAN Registration	43

2.2	Pending Litigation	43

2.2.1 	Pending Litigation	43

2.3 	Financial Situation	44

2.3.1	Historical Financial Performance	44

2.3.2	Average Annual Construction Turnover	44

2.4	Experience	46

2.4.1	General Construction Experience	46

2.4.2    Specific Construction Experience	46

(a) Contracts of Similar Size and Nature	46

(b)	Construction Experience in Key Activities	48

# 1. Evaluation

In addition to the criteria listed in ITB 36.2 (a) – (f) the following criteria shall apply:

Note:

Use the evaluation criteria listed below as appropriate and required for the project.

# 1.1	Adequacy of Technical Proposal

Evaluation of the Bidder's Technical Proposal will include an assessment of the Bidder's technical capacity, to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section 5 (Works Requirements).

Non-compliance with equipment and personnel requirements described in Section 5 (Works Requirements) shall not be grounds for bid rejection and such non-compliance will be subject to clarification and rectification prior to contract award.

# 1.2	Multiple Contracts

Pursuant to Sub-Clause 36.4 of the Instructions to Bidders, if Works are grouped in multiple contracts, evaluation will be as follows:

When, Works are grouped in multiple contracts and pursuant to Sub-Clause 36.4 of the Instructions to Bidders, the Employer will evaluate and compare Bids on the basis of a contract, or a combination of contracts, or as a total of contracts in order to arrive at the least cost combination for the Employer by taking into account discounts offered by Bidders in case of award of multiple contracts.

Qualification Criteria for Multiple Contracts:

The criteria for qualification shall be the sum of the minimum requirements for respective individual contracts as specified under items 2.3.2, 2.3.3, 2.3.4 and 2.4.2b.

With respect to the Contracts of Similar Size and Nature under item 2.4.2(a). of Section III, the evaluation shall be done as below:

N is the minimum number of contracts required as per Specific Construction Experience (2.4.2(a)).

V is the minimum value of a single contract as per Note (2) or (3) of 2.4.2 Specific Construction Experience

- Minimum requirements for combined contract(s) shall be the aggregate requirements for each contract for which the bidder has submitted bids as follows, and N1,N2,N3, etc. shall be different contracts:

Contract 1:  N1 contracts, each of minimum value V1;

Contract 2:  N2 contracts, each of minimum value V2;

Contract 3:  N3 contracts, each of minimum value V3;

----etc.

Or

- Total number of contracts is equal or less than N1 + N2 + N3 +--but the total value of all such contracts is equal or more than N1 x V1 + N2 x V2 + N3 x V3 +---.

# 1.3   	In Case, other than Multiple Contracts

Bidders have the option to Bid for any one or more Contracts. The contracts will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer, subject to the selected Bidder(s) meeting the required qualification which shall be the sum of the minimum requirements for respective individual contracts. Under this case, Contract shall be awarded based on Least Cost Combination to the Employer.

# 1.4	Completion Time

An alternative Completion Time, if permitted under ITB 13.2, will be evaluated as follows:

[Insert project specific requirements when permitted otherwise insert “Not Applicable”]

# 1.5	Alternative Technical Solutions

Alternative technical solutions, if permitted under ITB 13.4, will be evaluated as follows:

[Insert project specific requirements when permitted otherwise insert “Not Applicable”]

# 1.6  	Domestic Preference

1.6.1 In comparing domestic bids with foreign bids, a Domestic preference as per ITB 34.1 shall be granted to eligible domestic contractors, as defined below, in accordance with the following provisions.

- For application of domestic preference, all responsive bids shall first be classified into the following two categories:

- Category I: Bids offered by domestic contractors (domestic firms, intuitions, or company either in single or in joint venture (all partners)) and Joint Ventures eligible for the preference in accordance with the criteria set forth as follows:

Joint Ventures between a Domestic Contractor(s) and its foreign partner(s) shall eligible for the Domestic Preference Scheme only if domestic contractor(s) (domestic firms, intuitions, or company) have at least 25 % share in the Joint Venture., and

- Category II: Bids offered by other Contractors.

- If the Bid closest to the Average Bid Price is a bid from Category II, the next closest Bid from Category I that is up to 5% higher in price than the Bid from Category II, shall be selected for award.

# 1.7	Quantifiable Nonconformities, Errors and Omissions

[Insert project specific requirements]

The evaluated amount of quantifiable nonconformities, errors and/or omissions shall be determined by ascertaining the price of such effect on an equal basis by adjusting the same to the quoted price of the bid. A bid having minor deviations and having no material deviation to cause any serious effect upon the scope, quality, characteristics, terms and conditions, performance or any other requirements stated in the bidding documents and acceptable to the Employer can be considered to be substantially responsive.

# 2.	Qualification

# 2.1	Eligibility

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

# 2.1.1	Conflict of Interest

| No conflicts of interest in accordance with ITB Sub-Clause 4.3. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | Letter of Bid |
| --- | --- | --- | --- | --- | --- |

# 2.1.2	Government-owned Entity

| Applicant required to meet conditions of ITB Sub-Clause 4.5. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | Forms ELI -1, ELI - 2 with attachments |
| --- | --- | --- | --- | --- | --- |

# 2.1.3   Development Partner Eligibility [if applicable other mention “Not Applicable”]

| Not having been declared ineligible by Development Partner, as described in ITB Sub-Clause 4.4. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | Application Submission Sheet |
| --- | --- | --- | --- | --- | --- |

# 2.1.4	UN Eligibility

| Not having been declared ineligible based on a United Nations resolution or Employer’s country law, as described in ITB Sub-Clause 4.7. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | Letter of Bid |
| --- | --- | --- | --- | --- | --- |

# 2.1.5	Bidder’s Running Contracts

| Bidder’s Running Contracts not more than five (5) as described in ITB Sub-Clause 4.10. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | ELI-3 |
| --- | --- | --- | --- | --- | --- |

# 2.1. 6	VAT and PAN Registration

| - Domestic Bidder | Bidders required to meet conditions of ITB Sub-Clause 4.9. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | PAN and VAT registration certificate |
| --- | --- | --- | --- | --- | --- | --- |
| - Foreign Bidder | Bidders required to meet conditions of ITB Sub-Clause 4.9. | must meet requirement | existing or intended JV must meet requirement | must meet requirement | not applicable | Declaration to submit PAN and VAT Registration Certificate at the time of Contract agreement |

# 2.2	Pending Litigation

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

# 2.2.1 	Pending Litigation

| All pending litigation shall be treated as resolved against the Applicant and so shall in total not represent more than ….…(1) percent of the Applicant’s net worth. | must meet requirement by itself or as partner to past or existing JV | not applicable | must meet requirement by itself or as partner to past or existing JV | not applicable | Form LIT – 1 |
| --- | --- | --- | --- | --- | --- |

Note:

(1)	The percentage should normally be within the range of 50% to 100% of an Application's net worth.

# 2.3 	Financial Situation

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

# 2.3.1	Historical Financial Performance

| Submission of audited balance sheets and income statements, for the last ….(1)…… years to demonstrate the current soundness of the applicants financial position. As a minimum, a Bidder's net worth for the last year calculated as the difference between total assets and total liabilities should be positive. | must meet requirement | not applicable | must meet requirement | not applicable | Form FIN - 1 with attachments |
| --- | --- | --- | --- | --- | --- |

Note:

(1) 	The financial information provided by an Applicant should be reviewed in its entirety to allow a truly informed judgment, and the pass-fail decision on the financial position of the Applicant should be given on this basis. Balance sheet of the past three to five years period shall be asked according to the nature of the work.

# 2.3.2	Average Annual Construction Turnover

| Minimum average annual construction turnover of NPR ….……(2), calculated as total certified payments received for contracts in progress or completed, within best three years out of last ten fiscal years. | must meet requirement | must meet requirement | must meet . . . . (3). . . of the requirement | must meet . .(4) . . . . of the requirement | Form FIN - 2 |
| --- | --- | --- | --- | --- | --- |

Note:

2) The amount stated should normally not be less than 1.5 x V/T, the estimated annual turnover in the subject contract based on a straight-line projection of the  Engineer's estimated cost (V), over the contract duration (T) in year. The Engineer's estimated cost (V) is taken without VAT and contingencies but including provisional sum. Contract duration less than one year shall be considered one year. The multiplier of 1.5 may be reduced up to1 (one) in accordance with the size, nature and complexity of contracts.

Only the net amount shall be calculated after deducting the amount for VAT and such amount shall be adjusted wholesale price index of Nepal Rastra Bank.

(3)   Usually not less than 25 %

(4)   Usually not less than 40 %

| 2.3.3 Financial Resources |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Using Forms FIN - 3 and FIN - 4 in Section IV (Bidding Forms) the Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, and other financial resources, (other than any contractual advance payments) to meet the cash-flow requirement of … (5)….. | must meet requirement | must meet requirement | must meet ….(6)…. of the requirement | must meet ….(7)…. of the requirement | Form FIN - 3 |

Note:

(5) Construction cash flow requirement for a number of months  (to the nearest half-month), determined as the total time needed by the Employer to pay a contractor's invoice, allowing for (a) the actual time consumed for construction, from the beginning of the month invoiced, (b) the time needed by the Project Manager to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed three months for estimated cost (excluding Vat) more than NPR. 250 Millions and for estimated cost (excluding Vat) less than NPR. 250 Millions, the total period should not exceed 5 months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated contract cost.]

(6) Usually not less than 25 %

(7) Usually not less than 40 %

| 2.3.4 Required Bid Capacity |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| The bidding capacity of the bidder should be equal to or more than the NPR... (8)…… | must meet requirement | must meet requirement | must meet ……(9)…… of the requirement | must meet ……(10)…… of the requirement | Form FIN 4 and Form FIN - 5 |

(8) Equal to 80 to 100 % Engineer’s Estimate( without VAT and Contingencies but including Provision Sum) in round figure

(9)   usually not less than 25 %

(10)   Usually not less than 40 %

# 2.4	Experience

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | Joint Venture |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

# 2.4.1	General Construction Experience

| Experience under construction contracts in the role of contractor, subcontractor, or management contractor for at least the last ….(11)…… years prior to the applications submission deadline. | must meet requirement | not applicable | must meet requirement | not applicable | Form EXP -1 |
| --- | --- | --- | --- | --- | --- |

Note:

(11) 	Insert number of years in words and figures. The time period is normally 5 years , but may be reduced to not less than 3 years, according to the nature of works.

| # 2.4.2 Specific Construction Experience |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # (a) Contracts of Similar Size and Nature |  |  |  |  |  |
| (i) For Works with estimated value (without VAT & Contingency but including PS) up to NPR. 100 million |  |  |  |  |  |
| Participation as Prime contractor, management contractor, or subcontractor, in at least One (1) Contract within the last ten (10) years, with a value of at least NPR …..(12)…. that have been successfully or are substantially completed and that are similar to the proposed works. The similarity shall be based on the physical size, complexity, methods, technology or other characteristics as described in Section V, Works Requirements. | must meet requirement | not applicable | not applicable | must meet requirement | Form EXP – 2(a) |
| (ii) For Works with estimated value (without VAT & Contingency but including PS) above NPR. 100 million |  |  |  |  |  |
| Participation as Prime contractor, management contractor, or subcontractor, in at least One (1) Contract within the last ten (10) years, with a value of at least NPR …..(13)…. that have been successfully or are substantially completed and that are similar to the proposed works. The similarity shall be based on the physical size, complexity, methods, technology or other characteristics as described in Section V, Works Requirements. | must meet requirement | not applicable | not applicable | must meet requirement | Form EXP – 2(a) |
| (iii) For complex works with estimated value (without VAT & Contingency but including PS) up to NPR. 100 million** |  |  |  |  |  |
| Participation as Prime contractor, management contractor, or subcontractor, in at least One (1) Contract within the last ten (10) years, with a value of at least NPR …..(12)…. that have been successfully or are substantially completed and that are similar to the proposed works. The similarity shall be based on the physical size, complexity, methods, technology or other characteristics as described in Section V, Works Requirements. | must meet requirement | not applicable | at least one Contract within the last ten (10) years with a value of at least NPR …..(4)…. that have been successfully or are substantially completed and that are similar to the proposed works | must meet requirement | Form EXP – 2(a) |
| (iv) For complex works with estimated value (without VAT & Contingency but including PS) above NPR. 100 million** |  |  |  |  |  |
| Participation as Prime contractor, management contractor, or subcontractor, in at least One (1) Contract within the last ten (10)) years, with a value of at least NPR …..(13) …. that have been successfully or are substantially completed and that are similar to the proposed works. The similarity shall be based on the physical size, complexity, methods, technology or other characteristics as described in Section VI, Works Requirements. | must meet requirement | not applicable | at least one Contract within the last ten (10) years with a value of at least NPR …..(14)…. that have been successfully or are substantially completed and that are similar to the proposed works | must meet requirement | Form EXP – 2(a) |

Only the net amount worked out after deducting the amount for VAT shall be computed and such amount shall be adjusted according to the updated price index of the Nepal Rastra Bank.

**Complex works means those works involving complex technology such as tunnel, roads (asphalt concrete, Rigid pavement with high grade concrete etc.), major/special bridges (pre stress bridge, special type of bridges such arch bridge, cable stayed bridge, suspension bridge etc.), airport, large water supply projects, large irrigation projects and similar works. However in case of complex works like tunnel roads, airports, railway lines, hydropower projects, flyover, viaduct etc. for which experienced domestic bidders are not available in market, in order to enhance capability of domestic bidders, the qualification criteria (only for Joint Venture between foreign and domestic bidders) may be specified in a similar manner for non-complex works i.e. each partner’s requirement may be specified as “not applicable”

Note:

(12) Insert amount in US Dollar or Nepalese rupees, which is 40%  (in above round figure in thousand) of the estimated value (without VAT and contingencies but including provisional sum) of the subject contract.

(13) Insert amount in US Dollar or Nepalese rupees, which is 60% (in above round figure in thousand)  of the estimated value (without VAT and contingencies but including provisional sum) of the subject contract.

(14) Only in case of complex works, insert amount US Dollar or Nepalese Rupees which is 10% (in above round figure in thousand) of the estimated value (without VAT and contingencies but including provisional sum) of the subject contract.

# (b)	Construction Experience in Key Activities

| For the above or other contracts executed during the period stipulated in 2.4.2(a) above, a minimum construction experience in the following key activities: [list activities indicating, number or rate of production as applicable; for the key activity (ies) in the subject contract. The rates should be about 80% of the estimated production rates of the key activity(ies) in the subject contract as needed to meet the expected construction schedule with due allowance for adverse climatic conditions. Contract duration less than one year shall be considered one year for calculation of annual production rates.] | must meet all requirements | must meet all requirements | not applicable | not applicable | Form EXP-2(b) |
| --- | --- | --- | --- | --- | --- |

- Under Criterion 2.4.2 (a), the specified requirements define the similarity of contracts, whereas the key activities or production rates to be specified under Criterion 2.4.2 (b) define the required capability of the Bidder to execute key components of the Works. There shall be no inconsistency or duplication of requirements between Criteria 2.4.2(a) and 2.4.2(b).

- For the rate of production, the rate of production shall be on the basis of the average during the entire contract period.

- Only the activities having weightage 10 percent or more of the total estimated amount that should be manufactured or built by contractor should be considered as key activities

- Key activities or production rates to be specified shall not restrict innovation and better quality.

- Key activities or production rates of different contracts for a particular duration can be added while evaluating.

- While specifying key activities or production rates, it shall be assured and to be recorded by public entity so that sufficient bidders with required qualification are available in market for adequate competition

- Key activities or production rates to be specified shall be unambiguous e.g. environmental friendly, international/high standard, complex technology etc.

- While specifying Key activities or production rates, the similarity shall be based on the complexity, methods or technology to be adopted.

- The activities that can be sub-contracted or readily available in the market (e.g. lift, elevator, electrical works, special type of facilities etc.) shall not considered as key activities.

Section 4 - Bidding Forms

This Section contains the forms which are to be completed by the Bidder and submitted as part of his Bid.

Table of Forms

Letter of Technical Bid	52

Letter of Price Bid	54

Schedules	55

Bill of Quantities [Unit Rate Contract]	55

Schedules of Prices [Lump Sum Contract]	55

Tables of Adjustment Data	56

Bid Security	57

Technical Proposal Format	58

1. Personnel	59

Form PER – 1: Proposed Personnel	59

Form PER – 2:  Resume of Proposed Personnel	60

2. Equipment	61

3. Site Organization	62

4. Method Statement	62

5. Mobilization Schedule	62

6. Construction Schedule	62

7. Schedule of Subcontractors	62

8. Others (insert additional requirement if applicable]	63

Bidder’s Qualification	64

Form ELI – 1: Bidder’s Information Sheet	65

Form ELI - 2: JV Information Sheet	66

Form LIT - 1: Pending Litigation	68

Form FIN - 1: Financial Situation	69

Form FIN - 2: Average Annual Construction Turnover	70

Form FIN - 3:   Financial Resources	71

Form FIN – 4: Bid Capacity	72

Form FIN- 5:   Current Contract Commitments / Works in Progress	73

Form EXP – 1:  General Construction Experience	74

Form EXP – 2 (a):  Specific Construction Experience	75

Form EXP – 2 (b):  Specific Construction Experience in Key Activities	76

Letter of Technical Bid

The Bidder must accomplish the Letter of Bid in its letterhead clearly showing the Bidder’s complete name and address.

Date:

Bidding No.:

Invitation for Bid No.:

To:

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) Clause 8;

- We offer to execute in conformity with the Bidding Documents the following Works:

- Our bid shall be valid for a period of . . . .insert validity period as specified in ITB 18.1. . . days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our bid is accepted, we commit to obtain a performance security in accordance with the Bidding Document;

- Our firm, including any subcontractors or suppliers for any part of the Contract, have nationalities from eligible countries or any countries [insert the nationality of the Bidder, including that of all parties that comprise the Bidder if the Bidder is a consortium or association, and the nationality of each Subcontractor and Supplier]; and meet the requirements of ITB 3.7, &3.8  ,

- We, including any subcontractors or suppliers for any part of the contract, do not have any conflict of interest in accordance with ITB 4.3;

- We are not participating, as a Bidder or as a subcontractor, in more than one bid in this bidding process in accordance with ITB 4.3, other than alternative offers submitted in accordance with ITB 13;

- Our firm, its affiliates or subsidiaries, including any Subcontractors or Suppliers for any part of the contract, has not been declared ineligible by the law of Nepal or official regulations or by Development Partner (if applicable) or by an act of compliance with a decision of the United Nations Security Council;

- We are not a government owned entity / We are a government owned entity but meet the requirements of ITB 4.5;

- We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed;

- Commissions or gratuities, if any, paid or to be paid by us to agents relating to this bid, and to contract execution if we are awarded the contract, are listed below:

| Name and address of agents | Amount and currency | Purpose of commission or gratuity |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |
| [if none, state “none”] |  |  |

- We declare that, we including any subcontractors or suppliers for any part of the contract do not have any conflict of interest in the proposed procurement proceedings and we have not been blacklisted as per ITB 3.4 and punished for an offense relating to the concerned profession or business.

- We agree to permit the Employer/DP or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Employer.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section 5 Works Requirement) and our technical proposal, or as otherwise agreed with the Employer.

- We declare that we are solely responsible for the authenticity of the documents submitted by us. The document and information submitted by us are true and correct. If any document/information given is found to be concealed at a later date, we shall accept any legal actions by the Employer.

- We declare that we have not running contracts more than five (5) in accordance with   ITB 4.10.

- We declare that if the contract is awarded to us, financing for the execution of works under the contract will be available from legal and valid sources.

Name

In the capacity of

Signed

Duly authorized to sign the Bid for and on behalf of

Date

Letter of Price Bid

(Please Refer to Price Bid)

Schedules

Bill of Quantities [Unit Rate Contract]

Schedules of Prices [Lump Sum Contract]

(Please Refer to Price Bid)

Tables of Adjustment Data

(Please Refer to Price Bid)

Bid Security

##### Bank Guarantee

Bank’s Name, and Address of Issuing Branch or Office 
(On Letter head of the bank)

Beneficiary: .............................. name and address of Employer ……………………………………….

Date: ……………………………………………………………………………………………………...

Bid Security No.: ..........................................................................................................................................

We have been informed that . …………. .[insert name of the Bidder]  (hereinafter called “the Bidder”)

intends  to submit its bid (hereinafter called “the Bid”) to you for the execution of …………... name of

Contract . …………… under Invitation for Bids No. ……………… (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we…………………. . name of Bank. ………………..   hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . ………...amount in figures ………………………. (. …………..	.amount in words ……………….) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a)  has withdrawn or modifies its Bid during the period of bid validity specified by the Bidder in the Form of Bid; or

(b) does not accept the correction of errors in accordance with the Instructions to Bidders 
(hereinafter “the ITB”); or

(c)  having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Agreement, or (ii) fails or refuses to furnish the performance security, in accordance with the ITB.

(d)  is involved in fraud and corruption in accordance with the ITB

(e) changes the prices or substance of the bid while providing information pursuant to clause 27.1 of ITB; or

(f)  if the bidder fails to inform about the saturation of the maximum number of contracts as per ITB 4.11.

This guarantee will remain in force up to and including the date ………number…………days after the deadline for submission of Bids as such deadline is stated in the instructions to Bidders or as it may be extended by the Employer, notice of which extension(s) to the Bank is hereby waived. Any demand in respect of this guarantee should reach the Bank not letter than the above date.

This Bank guarantee shall not be withdrawn or released merely upon return of the original guarantee by the Bidder unless notified by you for the release of the guarantee.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

. . .Bank’s seal and authorized signature(s) . . .

Note:

The bid security of ………..……………. has been counter guaranteed by the Bank ……..………...	...…… on

…………...	...……..………. (Applicable for Bid Security of Foreign Banks).

Technical Proposal Format

- Personnel

- Equipment

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Schedule of Sub Contractors

- Others

1. Personnel

Form PER – 1: Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements for each of the positions listed in Section 5 (Work Requirements). The data on their experience should be supplied using the Form below for each candidate.

| No. | Name | Position* | Academic Qualification | Total Work Experience [Years] | Experience in Similar Works [years] |
| --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |
| 2. |  |  |  |  |  |
| 3. |  |  |  |  |  |
| 4. |  |  |  |  |  |
| 5. |  |  |  |  |  |

*As listed in Section 5 (Work Requirements)

Form PER – 2:  Resume of Proposed Personnel

The Bidder shall provide all the information requested below.

| Position |  |  |
| --- | --- | --- |
| Personal Information | Name | Date of Birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager/personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last twenty years in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| From | To | Company, Project, Position and Relevant Technical and Management Experience |
| --- | --- | --- |

2. Equipment

Form EQU: Equipment

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section 5 (Work Requirements). A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.   The Bidder shall provide all the information requested below, to the extent possible.

For the equipment under Bidder's ownership

| No. | Equipment Type and Characteristics | Total Nos. of Equipment under Bidder's Ownership | No. of Equipment engaged/proposed for ongoing/committed contracts | Nos. of Equipment proposed for this contract |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

- For the Equipment to be leased/hired

| No. | Equipment Type and Characteristics | Total Nos. of Equipment under the ownership of lease/hire provider | No. of Equipment engaged/committed for other works | Nos. of Equipment proposed to be leased/hired for this contract |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

| Type of Equipment |  |  |
| --- | --- | --- |
| Equipment Information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current Status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment Owned Rented Leased Specially manufactured |  |

The following information shall be provided only for equipment not owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | email |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

3. Site Organization

The Bidder shall show here in an Organogram format the organization of his site personnel showing clearly designated duties and responsibilities and the chain of command throughout the structure. Included in the chart shall be the names of respective personnel.

4. Method Statement

The Bidder shall provide here a brief description of how the Works are to be undertaken. The description shall indicate how each activities are to be undertaken.

5. Mobilization Schedule

The Bidder shall provide here a general description of the arrangements and methods which he proposes to adopt for the execution of the Works which shall include but not be limited to:-

- Mobilization period including periods required for establishing the Contractor’s offices, workshops etc. and the facilities required for the Engineer and his staff.

- Sources of Contractor’s equipment and mobilization periods for items of plant.

6. Construction Schedule

The Bidder shall provide here his proposed programme for construction of the Works within the Time for Completion.  The programme shall be presented in the form of a bar chart showing main construction activities with Milestones. Associated groups of construction equipment shall be listed.

7. Schedule of Subcontractors

The bidder shall enter in the following table a list of the sections and appropriate value of the work for which he proposes to use subcontractors, together with the names and addresses of the proposed subcontractors. The bidder shall also enter a statement of similar works previously executed by the proposed subcontractors, including description, location and value of work, year completed, and name and address of the employer/engineer.

| Item Nos. | Description of work | Approximate value (US$ or equivalent) | Name and address of Subcontractor | Statement of similar works executed |
| --- | --- | --- | --- | --- |

Notwithstanding such information the bidder, if awarded the Contract, shall remain entirely and solely responsible for the satisfactory completion of the Works.

8. Others (insert additional requirement if applicable]

Bidder’s Qualification

To establish its qualifications to perform the contract in accordance with Section 3 (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder.

Form ELI – 1: Bidder’s Information Sheet

| Bidder’s Information |  |  |
| --- | --- | --- |
| Bidder’s legal name |  |
| In case of JV, legal name of each partner |  |
| Bidder’s country of constitution |  |
| Bidder’s year of constitution |  |
| Bidder’s legal address in country of constitution |  |
| Bidder’s authorized representative (name, address, telephone numbers, fax numbers, e-mail address) |  |
| Attached are copies of the following original documents. 1. In case of single entity, articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1 and 4.2. 2. Authorization to represent the firm or JV named in above, in accordance with ITB 20.2. 3. In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1. 4. In case of a government-owned entity, any additional documents not covered under 1 above required to comply with ITB 4.5. |  |

Form ELI - 2: JV Information Sheet

Each member of a JV must fill in this form

| JV / Specialist Subcontractor Information |  |
| --- | --- |
| Bidder’s legal name |  |
| JV Partner’s or Subcontractor’s legal name |  |
| JV Partner’s or Subcontractor’s country of constitution |  |
| JV Partner’s or Subcontractor’s year of constitution |  |
| JV Partner’s or Subcontractor’s legal address in country of constitution |  |
| JV Partner’s or Subcontractor’s authorized representative information (name, address, telephone numbers, fax numbers, e-mail address) |  |
| Attached are copies of the following original documents. 1. Articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1 and 4.2. 2. Authorization to represent the firm named above, in accordance with ITB 20.2. 3. In the case of government-owned entity, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB 4.5. |  |

Form ELI - 3: Bidder’s Running Contracts in Nepal

Each member of a JV must fill in this form

| Bidder's Running Contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of office | Contract Identification no. | Date of issuance of Letter of Acceptance | Status of contract** | Date of Issuance of Taking Over Certificate*** |

*  Mention GON funded or DP funded or Other PE (Insert name) funded

** Mention "Yet to sign" if contract is not signed, "Running" if contract has been signed and contract is running and "Substantially completed" if taking over certificate has been issued.

** Insert date of issuance of taking over certificate if the awarded  contract has been substantially completed and taking over certificate has been issued.

Form LIT - 1: Pending Litigation

#### Each Bidder or member of a JV must fill in this form

| Pending Litigation |  |  |  |
| --- | --- | --- | --- |
| - No pending litigation in accordance with Criteria 2.2 of Section 3 (Evaluation and Qualification Criteria) - Pending litigation in accordance with Criteria 2.2 of Section 3 (Evaluation and Qualification Criteria) |  |  |  |
| Year | Matter in Dispute | Value of Pending Claim in US$ Equivalent | Value of Pending Claim as a Percentage of Net Worth |

Form FIN - 1: Financial Situation

Each Applicant or member of a JV must fill in this form

|  | ##### Financial Data for Previous 5 Years [in NPR or Equivalent US$] |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Year 1 | Year2 | Year3 | Year4 | Year5 |

Information from Balance Sheet

| Total Assets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Liabilities |  |  |  |  |  |
| Net Worth |  |  |  |  |  |
| Current Assets |  |  |  |  |  |
| Current Liabilities |  |  |  |  |  |

Information from Income Statement

| Total Revenues |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Profits Before Taxes |  |  |  |  |  |
| Profits After Taxes |  |  |  |  |  |
| - Attached are copies of financial statements (balance sheets including all related notes, and income statements) for the last two to five years, as indicated above, complying with the following conditions. - All such documents reflect the financial situation of the Applicant or partner to a JV, and not sister or parent companies. - Historic financial statements must be audited by a certified accountant. - Historic financial statements must be complete, including all notes to the financial statements. - Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted). |  |  |  |  |  |  |

Note:  Attested Financial reports, including balance sheets, profit and loss statements and auditors reports for the last 5 years should be attached.

In case of e-submission the attachments should not be uploaded but shall be submitted on notification by the Employer as per ITB 27.

Form FIN - 2: Average Annual Construction Turnover

Each Bidder or member of a JV must fill in this form

The information supplied should be the Annual Turnover of the Bidder or each member of a JV in terms of the amounts billed to clients for each year for work in progress or completed in NPR or in US Dollars in case of foreign bidders at the rate of exchange at the end of the period reported.

| ##### Annual Turnover Data for the Last 10 Years (Construction only) |  |  |  |
| --- | --- | --- | --- |
| Year | Amount Currency | Exchange Rate | US$ Equivalent |
| Average Annual Construction Turnover |  |  |  |

Form FIN - 3:   Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section III (Evaluation and Qualification Criteria).

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (in NPR) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Form FIN – 4: Bid Capacity

Each Bidder or member of a JV must fill in this form

Bid Capacity = [(5 x A) – B]

A = Average Annual Turnover of best three years out of last ten fiscal years.

B = Annual Value of the existing commitments and works (ongoing) to be completed, calculated from FIN-4.

| SN | Name of Bidder | Pan No. | A, in Million | B, in Million | Bid Capacity, in Million |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |

Total Bid Capacity:

Signature of Bidder

Form FIN- 5:   Current Contract Commitments / Works in Progress

Bidders and each partner to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

| Current Contract Commitments ( For Calculation of B with reference of FIN-3) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Name of Contract | Name of the Contractor/s | Employer's Contact Address, Tel, Fax | Contract Share in % (a) | Contract Amount in Millions (b) | Contract Date (yyyy-mm) (c) | Initial or Revised Contract Duration (months) (d) | Value of outstanding works [In Millions, NPR ]# (e) | Estimated Time in Month to Complete the outstanding works (f) = (c) + (d) – Date of Invitation of Bid (f) |
| 1 |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |

Signature of Bidder

# The  Outstanding Works means Contract Price (excluding Vat) minus Work Evaluated by Employer till the reference date. Bidder shall have to submit the relevant documentary evidence to substantiate the facts/figures.

Note 1: “B” shall be calculated as :  ,  If (f) is less than 12, then value of (f) shall be taken as 12.

Note 2: If Initial or Revised Contract Date is run out  with respect to Date of Invitation of Bid, the Estimated Time in Month to Complete the outstanding works shall be taken equal to 12 months.

Form EXP – 1:  General Construction Experience

Each Bidder or member of a JV must fill in this form

| ##### General Construction Experience |  |  |  |  |
| --- | --- | --- | --- | --- |
| Starting Month Year | Ending Month Year | Years | Contract Identification and Name Name and Address of Employer Brief Description of the Works Executed by the Bidder | Role of Bidder |

Form EXP – 2 (a):  Specific Construction Experience

Fill up one (1) form per contract.

| ##### Contract of Similar Size and Nature |  |  |  |
| --- | --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |  |
| Award Date |  | Completion Date |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Contract Amount | US$ ………………….. |  |  |
| If partner in a JV or subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone/Fax Number E-mail |  |  |  |
| ##### Description of the similarity in accordance with Criteria 2.4.2(a) of Section 3 |  |  |  |
| Note: The Employer should insert here contract size, complexity, methods, technology, or other characteristics as described in section 5 (Employer's Requirements) against which the bidder demonstrates similarity in the box on the right-hand-side. |  |  |  |

Form EXP – 2 (b):  Specific Construction Experience in Key Activities

Fill up one (1) form per contract

| ##### Contract with Similar Key Activities |  |  |  |
| --- | --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |  |
| Award Date |  | Completion Date |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Contract Amount | US$ ……………. |  |  |
| If partner in a JV or subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone Number Fax Number E-mail |  |  |  |
| ##### Description of the key activities in accordance with Criteria 2.4.2(b) of Section 3 |  |  |  |
| Note: The Employer should insert here production rate(s) for the key activity (activities) subject contract against which the bidder demonstrates in the box on the right-hand-side production rates achieved by him on previous contracts. |  |  |  |

PART II: EMPLOYER'S REQUIREMENTS

Section 5 - Works Requirements

This Section contains the Specification, the Drawings, and supplementary information that describe the Works to be procured.

Table of Contents

Scope of Work	79

Specifications	80

Drawings	82

Supplementary Information	83

Personnel Requirements	84

Equipment Requirements	84

Scope of Work

[Insert detail scope of works]

Specifications

Notes on the Specifications

A set of precise and clear specifications is a prerequisite for Bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their Bids. The specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured. Only if this is done will the objectives of economy, efficiency and fairness in procurement be realized, responsiveness of Bids be ensured, and the subsequent task of bid evaluation facilitated. The specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

Samples of specifications from previous similar projects are useful in this respect. The use of metric units is encouraged by the Donor Agency in case of Donor assisted projects. Most specifications are normally written specially by the Employer or Project Manager to suit the Contract Works in hand. The available standard specification of works of Ministry of Physical Planning and Works, DoLI and Other line Ministries can be adopted for respective civil construction works.

There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addenda should then adapt the General Specifications to the particular Works.

Care must be taken in drafting specifications to ensure that they are not restrictive. In the specification of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible. Where other particular standards are used, whether national standards of Nepal or other standards, the specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, will also be acceptable. The following clause may be inserted in the Special Conditions or Specifications.

Employers should decide whether technical solutions to specified parts of the Works are to be permitted. Alternatives are appropriate in cases where obvious (and potentially less costly) alternatives are possible to the technical solutions indicated in the bidding documents for certain elements of the Works, taking into consideration the comparative specialized advantage of potential bidders. For example:

The Employer should provide a description of the selected parts of the Works with appropriate references to Drawings, Specifications, Bill of Quantities, and Design or Performance criteria, stating that the alternative solutions shall be at least structurally and functionally equivalent to the basic design parameters and specifications.

Such alternative solutions shall be accompanied by all information necessary for a complete evaluation by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, proposed construction methodology, and other relevant details.

Sample Clause: Equivalency of Standards and Codes

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified will be accepted subject to the Project Manager’s prior review and written consent. Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the Project Manager at least 30 days prior to the date when the Contractor desires the Project Manager’s consent. In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.

These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the Procurement Documents. They should not be included in the final documents.

Drawings

Note:

- It is customary to bind the drawings in a separate volume, which is often larger than other volumes of the contract documents. The size will be dictated by the scale of the drawings, which must not be reduced to the extent that details are reduced illegible.

- A simplified map showing the location of the Site in relation to the local geography, indicating major roads, posts, airports, and railroads, is helpful.

- The construction drawings, even if not fully developed, must show sufficient details to enable bidders to understand the type and complexity of the work involved and the price the Bill of Quantities.

Supplementary Information

[Insert Supplementary Information if any]

Personnel Requirements

Using Form PER-1 and PER-2 in Section 4 (Bidding Forms), the Bidder must demonstrate it has personnel that meet the following requirements:

| No. | Position | Academic Qualification [When position demands] | Total Work Experience [Years] | Experience in Similar Works [years] |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

Equipment Requirements

Using Form EQU in Section 4 (Bidding Forms), the Bidder must demonstrate it has the key equipment listed below:

| No. | Equipment Type and Characteristics | Min. Number Requirement |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |
| 4. |  |  |
| 5. |  |  |

Section 6 – Preamble to the Bill of Quantities

(Please Refer to Price Bid)

PART III: CONDITIONS OF CONTRACT AND CONTRACT FORMS

Section 7 - General Conditions of Contract

The Conditions of Contract comprise two parts, this Section 7 - General Conditions of Contract (GCC) and the following Section 8 - Particular Conditions of Contract (PCC)

The General Conditions shall be the Conditions of Contract for Construction for Building and Engineering Works Designed by the Employer, prepared by the Fédération Internationale des Ingénieurs-Conseil, or FIDIC (FIDIC MDB Harmonized Construction Contract) available at http://www.fidic.org/

The Conditions of Contract have been prepared for an ad measurement (unit price or unit rate) type of contract and cannot be used for other types of contract.

Copies of the FIDIC Conditions of Contract can be obtained from:

FIDIC Secretariat

P. O. Box 86

1000 Lausanne 12

Switzerland

Web site: http://www.fidic.org

Section 8 – Particular Conditions of Contract (PCC)

Notes on the Particular Conditions of Contract

The PCC complement the GCC to specify data and contractual requirements linked to the special circumstances of the Country, the Employer, the Engineer and overall Project and the Contract works requirement. Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

Part A - Contract Data of the PCC should include data to complement the GCC in a manner similar to the way in which the Bid Data Sheet (BDS) complements the Instructions to Bidders (ITB).

Part B - Specific Provisions of the PCC are sample provisions which are used in other Projects in Nepal They are included here as reference for use by the Employer in preparing the Specific provisions. . They are not a complete standard set of provisions.. Project-specific provisions needs to be prepared in each case. Project specific requirement may require the sample provisions to be retained modified or deleted and new provisions added while preparing the Specific Provisions for each specific Contract.

Note: Clause numbers in the PCC correspond to those in the GCC.

# Part A – Contract Data

| Conditions | ### Ref. GCC | Data |
| --- | --- | --- |
| Employer’s name and address | 1.1.2.2 &1.3 | [ ... insert Employer’s name and address ... ] |
| Engineer’s name and address (if applicable) | 1.1.2.4 & 1.3 | [ ... insert Engineer’s name and address ... ] |
| Bank name (if applicable) | 1.1.2.11 | [ ... insert the name of the Development Partner financing the project if applicable ” ] |
| Donor’s name (if applicable) | 1.1.2.11 | [ ... insert Donor name.. if Applicable otherwise insert “Not Applicable”] |
| Borrower’s name | 1.1.2.12 | [ ... insert Borrower’s name if applicable] |
| Time for Completion | 1.1.3.3 | Replace the provision by “Time of Completion” means the time for completing the works or a Section under Sub Clause 8.2 [Time for Completion] or completion of work in percentage of contract amount, as stated in the Contract Data (with any extension under Sub Clause 8.4 [Extension of Time of Completion], calculated from the commencement date. [insert duration for time for completion of the whole of the Works and also the time for completion of sections or time for completion in terms of percentage of works, if applicable. If times (or dates) are to be specified for completion of various sections of the Works or for percentage of works, the applicable information should be listed in the table below for “Summary of Section completion or Percentage completion of the Works”] |
| Defects Notification Period | 1.1.3.7 | 365 days. |
| Sections | 1.1.5.6 | [If sections or percentage completion of works is used , refer to table Summary of Sections of the Works given below] |
| Electronic transmission systems (if applicable) | 1.3 | [.....insert Electronic transmission systems if applicable....] |
| Governing Law | 1.4 | The law of Nepal |
| Ruling language | 1.4 | English |
| Language for communications | 1.4 | English |
| Joint and Several Liability | 1.14 | The contractor shall not handover the responsibility of the contract to any one member or some members of Joint Venture or any other parties, not involved in the contract. |
| Time for access to the Site | 2.1 | days after Commencement Date [insert different dates if site is made available by sections] |
| Engineer’s Duties and Authority | 3.1(b)(ii) | Variations resulting in an increase of the Accepted Contract Amount in excess of_[insert % if required in Donor funded Project otherwise insert not Applicable] shall require approval of the Employer. |
| Performance Security | 4.2 | The performance security amount shall be 5 (five) percent of the bid price exclusive of VAT but including PS. If the bid for an Unit Rate Contract, which results in the Bid Price closest to the Average Bid Price, is seriously unbalanced, front loaded in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analysis for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analysis, taking into consideration the schedule of estimated Contract payments, the Employer may require that the amount of the performance security be increased in addition to mentioned above the expense of the Bidder as by 8% to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. Performance Security submitted to the Employer shall be “an Unconditional (on demand) Bank Guarantee” from a recognized Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law of Nepal acceptable to the Employer. The performance security form shall be in the format of the Bidding Document, Section 9 Contract forms. |
| Normal working hours | 6.5 | Normal working hours shall be 08.00 to 18.00 every day inclusive of two-hour break. Saturdays and Public Holidays are non-working days. |
| Extension of Time for Completion | 8.4 | The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information at least 21 days prior to the intended completion date. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. Along with full supporting information, the contractor shall also submit a revised work schedule and ensure that the Performance Security, Insurance, and Advance Payment Security (if any) remain valid. Within fifteen (15) days of the receipt of Letter of Extension of Intended Completion Date from the Employer, the contractor shall submit Performance Security, Advanced Payment Guarantee (if any) and Insurance Policy documents as required with extended validity. If the contractor fails to do so within the time mentioned above, the Contractor shall pay a fine at the rate of 0.01% of the final contract price (without VAT but including PS) per day for a maximum of fifteen (15) days. The Employer may deduct the fine from payments due to the Contractor. |
| Delay damages for the Works | 8.7 & 14.15(b) | The liquidated damage for whole of the works is 0.05 % of the final Contract Price per day, in the currencies and proportions in which the Contract Price is payable. If sectional or percentage completion mile stone s are specified then [ insert applicable liquidated damages will be as specified in the “Summary of Section of Works “ table given below] |
| Maximum amount of delay damages | 8.7 | 10 % of the final Contract Price. |
| Provisional Sums | 13.5.(b)(ii) | _______% [If there are Provisional Sums, insert a percentage for adjustment of Provisional Sums] |
| Adjustments for Changes in Cost; Table(s) of Adjustment Data | 13.8 | Period “n” applicable to the adjustment multiplier “Pn”: _”Not Applicable” [Add New paragraphs with the following texts at the end of Sub-Clause 13.8: 13.8.1“The base cost indices or prices shall be those prevailing on the day 30 days prior to the latest date for submission of bids. Current indices or prices shall be those prevailing 30 days prior to the period to which a particular Payment Certificate is related. If at any time the current indices are not available, provisional indices determined by the Engineer shall be used, subject to subsequent correction of the amounts paid to the contractor when the applicable indices become available. 13.8.2 Sources of Indices and Weightings: The sources of indices shall be those listed in the Bidding Forms- Table of Price Adjustment data, as approved by the Project Manager. Indices shall be appropriate for their purpose and shall relate to the Contractor’s proposed source of supply of inputs on the basis of which his Contract shall have been computed. As the proposed basis for price adjustment, the Contractor shall have submitted with his bid the tabulation of Weightings and Source of Indices in the Bidding Forms, which shall be subject to approval by the Project Manager. 13.8.3 Weightings: The weightings for each of the factors of cost given in the Bidding Forms shall be adjusted if, in the opinion of the Project Manager, they have been rendered unreasonable, unbalanced or inapplicable as a result of varied or additional work already executed or instructed under Clause 13.1 or for any other reason. 13.8.4 Subsequent Legislation: If, after the date 30 days prior to the latest date for submission of bids for the Contract, there occur changes to any National Statute, Ordinance, Decree, or other Law or any regulation or by-law of any local or other duly constituted authority, or the introduction of any such Statute, Ordinance, Decree, Law, regulation or by-law which causes additional or reduced cost to the Contractor, other than under the preceding sub-clauses of this clause, in the execution of the Contract, such additional or reduced cost shall, after due consultation with the Employer and the Contractor, be determined by the Project Manager and shall be added to or deducted from the Contract Price and the Project Manager shall notify the Contractor accordingly, with a copy to the Employer. Notwithstanding the foregoing, such additional or reduced cost shall not be separately paid or credited if the same shall already have taken into account in the indexing of any inputs to the Price Adjustment Formulae in accordance with the provisions of Sub-Clauses 13.8. If the contractor fails to complete the works within the specified completion time pursuant to Sub clause 8.2, adjustment of prices thereafter until the date of completion of the works shall be made using either the indices or prices relating to the specified time for completion, or the current indices or prices whichever is more favorable to the Employer. However if an extension of time is granted pursuant to Sub clause 8.4, the above provision shall apply to adjustments made after the expiry of such approved extension of time. The total payment for adjustment for changes in cost shall be limited to 25% of the initial contract price. |
| Total advance payment | 14.2 | ____% Percentage of the Accepted Contract Amount payable in the currencies and proportions in which the Accepted Contract Amount(excluding provisional sum and VAT) is payable [Insert number and timing of installments if applicable] |
| Repayment amortization of advance payment | 14.2(b) | [ insert _______%] Note: usually 30% of the amount of the Interim Payment Certificates. |
| Percentage of Retention | 14.3 | ___%___[insert as applicable for GoN and DP funded project] |
| Limit of Retention Money | 14.3 | ___%___ [insert as applicable for GoN and DP funded project] |
| Plant and Materials | 14.5 (b)(i) | If Sub Clause 14 5 applies : Plants and Materials for payment when shipped en route to the site………………..[insert list] |
|  | 14.5 (c)(i) | Plants and Materials for payment when shipped en route to the site………………..[insert list] |
| Minimum Amount of Interim Payment Certificates | 14.6 | % of the Accepted Contract Amount. |
| Maximum total liability of the Contractor to the Employer | 17.6 | [Select one of the two options below as appropriate] The product of [insert a multiplier less or greater than one] times the accepted Contract Price. 0r ………..[insert amount of the maximum total liability] |
| Periods for submission of insurance: a. evidence of insurance. b. relevant policies | 18.1 | [Insert period for submission of evidence of insurance and policy. Period may be from 14 days to 28 days.] a. evidence of insurance 21 days b. relevant policies 21 days |
| Maximum amount of deductibles for insurance of the Employer's risks | 18.2(d) | [insert maximum amount of deductibles] |
| Minimum amount of third party insurance | 18.3 | [insert minimum amount of third party insurance] |
| Date by which the DAB shall be appointed | 20.2 | NA |
| The DAB shall be comprised of | 20.2 | NA |
| List of potential DB sole members | 20.2 | NA |
| Appointment (if not agreed) to be made by | 20.3 | NA |
| Arbitration | 20.6(a) | For contracts with foreign contractors International arbitration shall be: (i) Administered by: [ ... insert institution ... ] (ii) Conducted in accordance with the rules of: [ … insert rules ... ]. |
|  | 20.6 (b) | Replace the provision by “ The place of Arbitration shall be Kathmandu, Nepal” |

Summary of Section completion or Percentage completion of the Works

| Section Name/Description Or Percentage completion (Sub-Clause 1.1.5.6) | Time for Completion (Sub-Clause 1.1.3.3) | Damages for Delay (Sub-Clause 8.7) |
| --- | --- | --- |

Part B  -  Specific Provisions

{The following sample provisions are included here as reference for use by the Employer in preparing the Specific provisions.. They are not a complete standard set of provisions. Project-specific provisions needs to be prepared in each case. Project specific requirement may require the sample provisions to be retained modified or deleted and new provisions added while preparing the Specific Provisions for each specific Contract]

| General Conditions | ### Ref.GCC | Data |
| --- | --- | --- |
| Base Date | 1. 1. 3 | Delete 1.1.3 “Base Date” and substitute as follows: “Base Date” means the date 30 days prior to the latest date for submission and completion of the Tender |
| Contract Agreement | 1.6 | Replace the first line of the paragraph by the following: “The parties shall enter into a Contract Agreement within 15 days after the Contractor receives the Letter of Acceptance. |
| Assignment | 1.7 | Add the following text at the end of Sub-Clause 1.7: “Any charge to the legal or beneficial shareholding of the Contractor or in any joint venture partnership or consortium which would have the effect of changing the effective control of the Contractor shall be deemed to be an assignment requiring the consent of the Employer under this clause.” |
| Care and Supply of Documents | 1.8 | Add the following text at the end of Sub-Clause 1.8: Irrespective of the above, the Contractor shall be responsible for the production of detailed construction drawings as may be necessitated by his work program pursuant to Sub-Clause 8.3 and as the Engineer may deem necessary for the proper execution of the Works. The Contractor shall supply two copies of draft prints of all such detailed construction drawings for the Engineer’s review and when approved by the Engineer shall supply six final prints together with a reproducible copy on computer disk or as may be otherwise approved by the Engineer. |
| Inspection and Audit of the Bank | 1.15 | Replace the Provision by the following: “Inspection and Audit of the Bank or Employer The Contractor shall permit the Bank or employer and /or persons appointed by the Bank/Employer to inspect the Site and /or the Contractor’s accounts and records audited by auditors appointed by the Bank/Employer if required by the Bank/Employer. “ |
| Engineer’s Duties and Authority | 3.1 | Add the following provisions at the end of Sub Clause 3.1: (e) Approving subcontracting of any part of the Works as per Sub-Clause 4.4 (f) Issuing the Notice for Commencement of the Works as per Sub-Clause 8.1 (g) Fixing Rates or Prices as per Sub-Clause 13: |
| Contractor’s General Obligations | 4.1 | Add the following paragraph at the end of sub clause 4.1(d): The Contractor shall also be responsible for the preparation of “As Built” drawings of all completed permanent works. The date by which “as built” drawings are required is: …………[For GoN funded: insert 30 days after work acceptance date, For DP funded: insert as per DP guidelines]. The Contractor shall supply two copies of draft prints of all such “As Built” drawings for the Engineer’s review and when approved by the Engineer, shall supply six final prints together with a reproducible copy in electronic format or as may be otherwise approved by the Engineer. The Contractor shall, where applicable, comply with the requirements stated in the Environmental Management Plan when provided in the Contract Document. |
| Performance Security | 4.2 | Delete and replace the second paragraph with the following text: The Contractor shall deliver the Performance Security to the Employer within fifteen (15) days after receiving the Letter of Acceptance and shall, send a copy to the Engineer. The Performance Security shall be denominated in the types and proportions of currencies in which the Contract Price is payable. The Contractor shall notify the Engineer when providing the Performance Security to the Employer. The Performance Security shall be issued either (a) by a bank located in Nepal or (b) directly by a foreign bank through a counter guarantee by a bank in Nepal. |
| Subcontractors | 4.4 | Add new text to this Sub-Clause 4.4, after item (d) as follows: (e) In the event of approved subcontracting the Contractor shall ensure that Subcontractors do not further sub-let their contract; (f) The Contractor shall not terminate the engagement of a subcontractor without the prior written consent of the Employer.” g) The Contractor shall keep a log showing the following information on the Sub Contractors, suppliers and transporters engaged in the contract works: - Name and Address - Copy of Sub Contracting Agreement - Works and value contract - Commencement and completion dates - Copy of payment certificates h) The contractor shall give prior notice to the Employer clearly specifying the nature, scope, and responsibilities of the work to be performed, to engage other subcontractors, material suppliers, equipment suppliers, service providers, or other persons or entities during the implementation of the contract. i) Before notifying the Employer as per item (h), the contractor shall enter into a written agreement with the subcontractors, material suppliers, equipment suppliers, service providers, or other persons or entities clearly specifying the scope of work, responsibilities, quality requirements, duration, payment terms, security, labor-related obligations, and conditions relating to performance of the work. j) Any subcontracting arrangement shall not relieve the Contractor of any of its obligations or liabilities under the Contract. k) The contractor shall provide the Employer with details of the payments made to the subcontractors, material suppliers, equipment suppliers, service providers, or other persons or entities engaged. i) If the contractor is found not to have made payment to the subcontractor, material suppliers, equipment suppliers, service providers, or other persons or entities engaged in accordance with the terms of the agreement, the Employer may determine the amount payable to such subcontractor, material suppliers, equipment suppliers, service providers, or other persons or entities and make payment to them from any remaining dues to be paid to the contractor, retention money, or forfeited performance security. |
| Co-operation | 4.6 | Add the following text after the final paragraph: “The provisions of Sub-Clause 4.6 notwithstanding, the Contractor shall allow free passage to other contractors working under contract to the Employer through and over the Site in the furtherance of their obligations under their contracts.” |
| Site Data | 4.10 | At the end of the Sub-Clause add new paragraph with the following text: “Site Data made available by the Employer in accordance with Sub-Clause 4.10 [Site Data] shall be deemed to include data listed elsewhere in the Contract as open for inspection at [Insert office name]”. |
| Rights of Way and Facilities | 4.13 | Insert the following text as the first paragraph of Sub-Clause 4.13: “The Contractor shall ascertain the location of all existing public utilities and other structures which may be encountered during the execution of the Works. He shall temporarily support or divert and subsequently reinstate all such utilities and structures as necessary and to the satisfaction of the Engineer. As soon as any such utilities or structure is encountered during the performance of the Contract, the Contractor shall make a record of the location and description of such service or structure and shall send the same forthwith to the Engineer. Where permanent diversion or support of such service or structure is rendered necessary as the unavoidable result of the execution of the Works in accordance with the Contract, the Engineer after consultation with the Employer will instruct the Contractor regarding the works to be carried out and the Contractor shall be paid the costs thereof in accordance with Clause 13 hereof if the work is not already apart of the contract.”. |
| Progress Report | 4.21 | Insert the following text after the last paragraph of the Sub Clause 4.21: “The Contractor shall keep a Site Diary wherein full details of all work carried out each day shall be recorded. The Site Diary may be prepared in sections relating to different parts of the works being carried out in different locations if applicable. The Contractors shall submit a copy of the Site Diary progress record every week to the Engineer. |
| Fossils | 4.24 | Insert the following text after the first paragraph: All materials and things of any kind obtained from excavations or found on or under the Site, or under any additional Site which the Contractor may be allowed to occupy, shall remain the property of the Government and shall not be used in the works or sold or otherwise disposed of without the written authority of the Engineer unless otherwise expressly provided in the Specification. |
| Site Meetings | 4.25 | Add new Sub-Clause 4.27 with the following text: The Engineer shall arrange regular site meeting and prepare the minutes of the meetings. The Engineer shall summon all parties concerned to the first Site Meeting where the date, time and place of future meetings shall be decided. It is the duty of the Contractor or his Representative to participate in the Site Meetings. The purpose of the Site Meetings is to co-ordinate the Works with the Contractor, to review the progress of the Works in relation to the Programme and to record understandings and agreed arrangements regarding the conduct and execution of the Works. Agreements recorded in Minutes of the Site Meetings are binding on all parties, if objections to the minutes have not been given in due time. Any objections to the Minutes of a Site Meeting shall be raised in writing at the next Site Meeting and in any case not later than 4 weeks after the meeting to which the Minutes refer. If the Contractor at this time has not received the Minutes of the Site Meeting, the objection must be given in writing to the Engineer no later than 4 working days after the subsequent receipt of the said Minutes. The Minutes of the Site Meetings shall be numbered consecutively. Minutes shall be deemed to have been received by the Contractor unless the Contractor gives notice at the following meeting that the Minutes were not received and there is no evidence to the contrary |
| Domestic Preference Security | 4.26 | Add new Sub-Clause 4.28: If the Contractor consists of a joint venture which is awarded the Contract through the application of the domestic preference, the Contractor: (i) throughout the execution of the Contract, shall not modify the work-sharing characteristics of the joint venture with which it satisfied the criteria of eligibility for the award of the Contract under domestic preference; and (ii) concurrently with the above Performance Security, shall provide security ("the domestic preference security") to guarantee that such characteristics of the joint venture will not be so modified. |
| Rates of Wages and Conditions of Labour | 6.2 | Insert the following text after the first paragraph: The Contractor’s scales of wages shall be such as to ensure that there is no differentiation between wages for men and women for work of equal value. The contractor shall enroll the labourers, employees, or other workforce engaged in such work in the Social Security Fund in accordance with prevailing laws. The contractor shall be responsible to disburse the remuneration, benefits, and other payments of the labourers, employees, or workforce into the bank account of the concerned individual. |
| Labour Laws | 6.4 | Add the following text at the end of Sub-Clause 6.4: The Contractor and sub-contractors shall comply with all applicable laws. |
| Commencement of Works | 8.1 | The Commencement date shall be [insert number] days after the Contractor receives Letter of Acceptance. The requirements of Sub-Clauses 8.1 (b) and 8.1 (d) shall not be precedent conditions to Commencement of the Works. |
| Time for Completion | 8.2 | Insert the following additional text after the last bullet : “c) Handing over all documents that are required to be delivered to the Employer prior to the Taking –Over Certificate being issued as stated in the Employer’s Requirements.” |
| Extension of Time of Completion | 8.4 | Add the following text at the end of Sub-Clause 8.4: The granting of an extension of time for completion shall not entitle the Contractor to any additional payment. Where, in the opinion of the Contractor, additional costs have been incurred as a result of the cause or the event for which an extension of time for completion has been granted, such costs shall be well documented and may be claimed separately, in accordance with the provisions of Clause 20.1. |
| Bonus | 8.13 | Add new Sub Clause 8.13: “The Contractor shall be paid a bonus calculated at the rate of [insert …..% ] of the final contract price] for each day that the completion of the works is earlier than the Time of Completion pursuant to GCC 8.2. The total amount of Bonus shall not exceed [insert …… % ] of the final contract price. |
| Taking Over of the Works and Sections | 10.1 | Replace (a) of Paragraph 3(three) by - issue the Taking-Over Certificate to the Contractor, stating the date on which the Works or Section were completed in accordance with the Contract, if physical progress of works is at least ninety (90) percent in accordance with the Contract except for any minor outstanding work and defects which will not substantially affect the use of the Works or Section for their intended purpose (either until or whilst this work is completed and these defects are remedied); or |
| Advance Payment | 14.2 | If the advance provided under GCC 14.2 is not repaid due to non-performance of the works under the contract, by the Contractor within the time period specified in the Contract, the Employer shall recover the advance by enforcing the bank guarantee as provided under GCC 14.2, and shall also recover interest on the advance amount from the Contractor at a rate of 10%. |
| Payment of Retention Money | 14.9 | Insert Paragraph 2 (two) and 3 (three) after Paragraph 1 (One) as follows: (2) the Contractor may substitute retention money with an unconditional bank guarantee issued from Commercial Bank or Financial Institution eligible to issue Bank Guarantee as per prevailing Law if: (a) at least eighty (80) percent of the whole works have been completed, (b) progress of the works is satisfactory in accordance with the Contract as per approved work schedule (c) it can be assured that the works can be completed at the intended completion date (3) If retention money is substituted by bank guarantee in accordance with clause 54.2, the bank guarantee shall be submitted either using the Retention Money Security Form included in Section 9 (Contract Forms) or in another Form acceptable to the employer. The validity of the bank guarantee shall be at least one month more than the end of defect liability period. |
| Termination By Employer | 15.2 | Add Sub clause (g), (h), (i) The Employer may terminate the Contract at any time if the contractor: - does not commence the work as per the Contract, - abandons the work without completing, - fails to achieve progress as per the Contract. - fails to submit Performance Security, Advanced Payment Guarantee (if any) and Insurance Policy documents with extended validity within the time prescribed pursuant to GCC 8.4. |
| Corrupt or Fraudulent Practices | 15.6 | Replace sub-clause: (a; (b); (c) and (d) by: (a) - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; - “fraudulent practice” means any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; - “coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; - “collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party. - “obstructive practice” means: - deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a GoN/DP investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or - acts intended to materially impede the exercise of the GoN’s/DP’s inspection and audit rights provided for under sub-clause 1.15 - will sanction a firm or individual, including declaring ineligible, for a stated period of time, to be awarded a GoN/DP-financed contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for, or in executing, a GoN/DP-financed contract (c) The contractor shall be prosecuted for offenses under prevailing criminal laws, if the contractor: (i) Misuses the Advance Payment or payments received from the Employer; (ii) Receives payment by submitting false information or documents; (iii) Abandons the works before completion; (iv) Commits a serious violation of the contract; or (v) Causes loss or damage to the Purchaser. |
| Insurance of the Works and Contractor’s Equipment | 18.2 | The Insuring Party shall be the Contractor. |
| Insurance of the Works and Contractor’s Equipment | 18.2 | Add the following text after Sub-paragraph 18.2 (e)(iv): It shall be the responsibility of the Contractor to notify the insurance company of any change in the nature and extent of the Works and to ensure the adequacy of the insurance coverage at all times during the period of the Contract. |
| Consequence of Force Majeure | 19.4 | Replace the provision of Sub Clause 19.4 (b) as follows: If the event or circumstances is of the kind described in sub-paragraphs (i) to (iv) of Sub Clause 19.1[Definition of Force Majeure] and, .in the case of sub paragraphs (ii) and (iv), occurs in the Country, payment of any such cost. In the case of sub paragraph (iii) occurs then cost compensation shall be applicable only if the Force Majeure situation exists for more than three consecutive days and the cost compensation shall only made for the cost incurred during the period after the first 3 days . However if the total Force Majeure situation exceeds 7 days period in a calendar month then the cost compensation shall be applicable for the period in excess of seven days even if the Force majeure situation did not exist continuously for more than three days . |

| Customs and Tax Provisions for Contractors of Donor Funded Projects if it is an requirement | 21 | Insert New Clause: |
| --- | --- | --- |
| General | 21.1 | (a) Unless otherwise specifically declared in the Contract Documents, the prices bid by the Contractor and its suppliers and Subcontractors shall include business taxes and other taxes that may be levied in accordance with the laws and regulations in force or in effect in Nepal as of 30 days prior to the closing date for submission of tenders in the Employer’s country on the Equipment, Plant, materials and supplies (permanent, temporary and consumables) acquired for the purpose of the Contract and on the services performed under the Contract. Whatsoever provisions made in the Contract shall not relieve the Contractor, its suppliers and Subcontractors from their responsibility to pay income tax that may be levied in the Employer’s country on profits made by the Contractor, its suppliers and Subcontractors in respect of the Contract. (b) In the event that the origin of any of the Contractor’s or its Subcontractors’ or the nominated subcontractors’ plant, equipment and materials is India, the above provisions for the exemption of customs duties and VAT as is mentioned in this Clause shall be applied only under the following conditions. Failure to comply with these conditions will result in application of normal customs duties, VAT as per prevailing rules and regulations of the Government of Nepal. - should the Contractor request payment in Indian Currency, the equipment and materials must have been imported under the ‘Duty Refundable Procedures (DRP)’ - should the Contractor request payment in other convertible currencies, the equipment and materials must have been imported under ‘In Bond Transfer Procedures’. |
| Staff Income Tax | 21.2 | The Contractor’s staff, personnel and labourers, and those of its Subcontractors, will be liable to pay personal income taxes in the Employer’s country, irrespective of whether they be local or foreign nationals, on income earned including salaries and wages as applicable under the laws and regulations of Nepal. The Contractor shall perform such duties in regard to Tax Deduction at Source (TDS) thereof as may be applicable by such laws and regulations. |
| Import License | 21.3 | The Contractor shall inform the Employer and the Engineer in writing the details of the equipment and materials to be imported into Nepal for use on the Works at least 45 days prior to arrival of shipment at disembarkation port, and shall submit a formal written request for assistance from the Employer for importation processing. The Employer will assist the Contractor to obtain the necessary permits for import such equipment and materials into Nepal. Import license fees or any other charges shall be at the cost of the Contractor. The Contractor shall be responsible for transport from the Port of Disembarkation to the Site or location of the Works. The Contractor shall be fully responsible to determine these rates and the amount at the time of preparing tender document and include such costs in its bids. In failing to do so, the Employer shall not be liable to pay such costs and the Contractor shall pay such charges as local or any customs authorities en-route may impose, which will not be an eligible item for refund from the Employer. |
| Duties on Equipment, Plant, Materials and Supplies (Re-exportable Items) | 21.4 | (a) Notwithstanding the provisions of this document, Contractor’s Plant and Equipment, including essential tools thereof, imported for the sole purpose of executing the Contract on condition of re-export upon completion of the Works, shall be exempt from payment of customs duties, VAT and other applicable taxes. However, the Contractor shall deposit the amount or provide a Bank Guarantee to the G/N Customs Office equal to the amount of customs duties and other taxes as per the prevailing laws, rules and regulations of Nepal for those imported items of equipment, plant, materials and supplies at the time of import. Such deposited amount shall be refunded, or the Bank Guarantee cancelled by the Employer after submission to the Employer of the re-export certificate issued by the Customs Department. (b) Any Plant, materials or supplies imported by the Contractor and used in the Works or for the performance of the Works shall be taken out of Nepal within 90 (ninety) days of the completion of the Works. If the Contractor disposes of or consumes any equipment, spare parts, unused materials or supplies within Nepal, it shall pay all customs duties, VAT, income tax on the sales proceeds and taxes applicable on such items under the laws and regulations of Nepal in force. |
| Duties on Equipment, Plant, Materials and Supplies (Consumable Items) | 21.5 | (a) Equipment, plant, materials and supplies, imported by the Contractor for execution of the Works, shall be subject to payment of customs duty at a special rate of one percent (1%) of CIF or Customs entry point value. This customs duty shall be paid by the Contractor at the time of import and will be reimbursed by the Employer to the Contractor upon submission of the original receipt issued by the Customs Department. (b) Customs Duties at the rate of one (1%) percent shall be imposed on the spare parts of the Contractor’s equipment and plant which are imported for the execution of the works, up to the amount of 10 (ten) percent of the CIF or Customs entry point value of each plant and equipment. If the value of imported spare parts exceeds 10 (ten) percent value of each equipment and plant, Contractor should pay taxes and duties in accordance with the prevailing laws and regulations of Nepal. The Employer shall not reimburse such customs duties, VAT and other taxes paid by the Contractor. (c) The Contractor shall maintain records satisfactory to the Employer documenting use of all Plant, materials and supplies imported into and/or procured for the performance of the Works. If any of such Plant, materials and/or supplies, imported into Nepal or otherwise supplied to the Project at a special or preferential rate of Customs Duties or taxes, are misused or found to be used or appropriated for any purposes other than the Project, the Contractor shall be held fully responsible, and liable to pay customs duties, VAT and other taxes and/or any penalties as may be imposed in accordance with the prevailing laws and regulations of Nepal. |
| Duties & Taxation on Goods | 21.6 | (a) VAT shall be imposed according to prevailing laws and regulations of GoN, on all materials and equipment purchased for the use in the contract Works. The Contractor shall submit request with VAT bills to the VAT office of GoN for reimbursement of the paid VAT within the prescribed time. |
| Income Tax | 21.7 | (a) Income tax assessed in accordance with the prevailing Income Tax Act of Nepal and as per the provision of specific Double Taxation Agreement, shall be imposed on the Contractor, its subcontractor and nominated subcontractor. An advance income tax as per the prevailing Income Tax and Finance Act shall be deducted from the monthly progress payments of the Contractor. |
| Duties, Taxes regulations etc. | 21.8 | (a) The Contractor shall pay all duties, taxes, fees and contributions levied in Nepal in Nepalese Rupees as directed by the relevant governmental department or office or any other local statutory agency or body in accordance with the relevant rules and regulations. (i) The provisions of the clause shall apply equally to foreign subcontractors or nominated subcontractors of the Contractor employed for the Works. (ii) The Contractor and any foreign subcontractors or nominated subcontractors employed on the Works, if not already registered in Nepal, shall be required to get registered with the Inland Revenue Department (IRD) for the purpose of the Contract, which shall be undertaken within 30 days after signing of the Contract Agreement. The Contractor, subcontractor or the nominated subcontractor shall submit Certified copies of the Registration Certificate(s) to the Engineer within 14 days of registration. (iii) Other local fees and charges (toll taxes) shall be applied in accordance with the prevailing laws and regulations of Nepal. |
| Royalties for Extraction of Aggregates, etc. from River Bed | 21.9 | The Contractor shall pay, and shall not be entitled to the reimbursement of the costs of, all charges and royalties levied in connection with the extraction of aggregates such as sand, stone/boulders, gravel, etc. from the river beds or from quarry sites or borrow pits and in connection with the winning of borrow material. Such charges will be levied by the local District Development Committee (DDC) or the Village Development Committee (VDC) or by other local committees in accordance with such regulations as may be in force at the time. |
| Use of Explosives | 22 | Insert New Clause: |
| Compliance with Regulations for Explosives | 22.1 | The Contractor shall comply with all relevant ordinances, instructions and regulations which the Government, or other person or persons having due authority, may issue from time to time regarding the handling, transportation, storage and use of explosives. |
| Permission for Blasting | 22.2 | The Contractor shall at all times maintain full liaison with and inform well in advance, and obtain such permission as is required from all Government authorities, public bodies and private parties whatsoever concerned or affected, or likely to be concerned or affected by blasting operations. |
| Engineer’s Approval for Use of Explosives | 22.3 | No explosives of any kind shall be used by the Contractor without the prior consent of the Engineer in writing and the Contractor shall provide, supply, handle, store and transport all explosives, ancillary materials and stores and all other things of every kind whatsoever required for blasting operation, all at his own expense in a manner approved in writing by the Engineer and acceptable to the police and military authorities. |
| Records of Explosives | 22.4 | Throughout the execution of the Contract, the Contractor shall account, on a continuous basis, to the satisfaction of the Engineer and the police and military authorities for all explosives brought on to the Site and for all explosives consumed in the Works. The Contractor shall remove all unused explosives from the Site on completion of the Works or shall dispose of such explosives in a manner acceptable to the police and military authorities. |

Section 9 - Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Table of Forms

Letter of Intent	105

Letter of Acceptance	106

Contract Agreement	107

Performance Security	108

Advance Payment Security	109

Schedule of Payment Currencies	115

Letter of Intent

[on letterhead paper of the Employer]

. . . . . . . date. . . . . . .

Notes on Letter of Intent

The issuance of Letter of Intent is the information of the selection of the bid of the successful bidder by the Employer and for providing information to other unsuccessful bidders who participated in the bid as regards to the outcome of the procurement process. This standard form of Letter of Intent to Award should be filled in and sent to the successful Bidder only after evaluation  and selection of substantially responsible evaluated bid closest to the Average Bid Price

To:	. . . . . . . . . .   name and address of the Contractor . . . . . . . . . .

Subject:	. . . . . . . . . .  Issuance of letter of intent to award the contract  . . . . . . . . . .

This is to notify you that, it is our intention to award the contract ………. dated …….…….. for execution of the  . . . . . . . . .name of the contract and identification number, as given in the Contract Data/SCC to you as your bid price . . . . . . . . .amount in figures and words in Nepalese Rupees/US$ ………………. as corrected and modified in accordance with the Instructions to Bidders is hereby selected as substantially responsive evaluated bid closest to the Average Bid Price

Authorized Signature:

Name:

Title:

CC:

[Insert name and address of all other Bidders, who submitted the bid]

[Notes on Letter of Intent

The issuance of Letter of Intent is the information of the selection of the bid of the successful bidder by the Employer and for providing information to other unsuccessful bidders who participated in the bid as regards to the outcome of the procurement process. This standard form of Letter of Intent to Award should be filled in and  sent to the successful Bidder only after evaluation   and selection of substantially  responsible evaluated bid closest to the Average Bid Price.]

Letter of Acceptance

[on letterhead paper of the Employer]

. . . . . . . date. . . . . . .

To:	. . . . . . . . . .   name and address of the Contractor . . . . . . . . . .

Subject:	. . . . . . . . . .   Notification of Award

This is to notify that your Bid dated . . . . date . . . .  for execution of the . . . . . . . . . .name of the contract and identification number, as given in the Contract Data/SCC . . . . . . . . . . for the Contract price of  the equivalent of [iamount in figures and words in the currency…….………….], as corrected in accordance with the Instructions to Bidders is hereby accepted by our Agency..

You are hereby instructed to contract this office to sign the formal contract agreement within 15 days. As per the Conditions of Contract, you are also required to submit Performance Security, as specified in SCC, consisting of a Bank Guarantee in the format included in Section 9 (Contract Forms) of the Bidding Document.

The Employer shall forfeit the bid security, in case you fail to furnish the Performance Security and to sign the contract within specified period.

Authorized Signature:

Name and Title of Signatory:

Contract Agreement

THIS AGREEMENT made the . . . . . .day of . . . . . . . . . . . . . . . . ., . . . . . . ., between . . . . . name of the Employer. . . . .. . . . . (hereinafter “the Employer”), of the one part, and . . . . . name of the Contractor. . . . .(hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as . . . . . name of the Contract. . . . .should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement.

-	the Letter of Acceptance;

-	the Letter of Bid;

-	the Addenda Nos . . . . . insert addenda numbers if any. . . . .

-	the Special Conditions;

-	the General Conditions;

-	the Specification;

-	the Drawings;

-	Bills of Quantities (BOQ);

-	Table of Price Adjustment Data;

-	the completed Schedules; and

-	Any other document

3.	In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works  and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of . . . . . NEPAL. . . . .on the day, month and year indicated above.

Signed by 		Signed by

for and on behalf of the Employer		for and on behalf the Contractor

in the presence of 		in the presence of

Witness, Name, Signature, Address, Date		Witness, Name, Signature, Address, Date

Performance Security

Bank’s Name, and Address of Issuing Branch or Office

Beneficiary: 	Name and Address of Employer

Date:

Performance Guarantee No.:

We have been informed that . . . . . name of the Contractor. . . . .  (hereinafter called "the Contractor") has  entered into Contract No. . . . . . reference number of the Contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of Works. . . . .  (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we . . . . . name of the Bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) such sum being payable in Nepalese Rupees, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the . . . . . Day of . . . . . . . . . . , . . . . . .  **, and any demand for payment under it must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . 
Seal of Bank and Signature(s)

Note:  All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

* The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Contract in Nepalese Rupees.

** Insert the date thirty days after the end of Defect Notification Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee.

Advance Payment Security

Bank’s Name, and Address of Issuing Branch or Office

Beneficiary: 	Name and Address of Employer

Date:

Advance Payment Guarantee No.:

We have been informed that . . . . . name of the Contractor. . . . .  (hereinafter called "the Contractor") has  entered into Contract No. . . . . . reference number of the Contract. . . . .   dated . . . . . . . .with you, for the execution of . . . . . . name of contract and brief description of Works. . . . .  (hereinafter called "the Contract").

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum  . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) is to be made against an advance payment guarantee.

At the request of the Contractor, we . . . . . name of the Bank. . . . .  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of . . . . . name of the currency and amount in figures*. . . . . . (. . . . . amount in words. . . . .  ) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number . . . . . Contractor’s account number. . . . .   at . . . . . name and address of the Bank. . . . .  .

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that eighty (80) percent of the Contract Price has been certified for payment, or on the . . . day of . . . . . . . , . . . . .**, whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

. . . . . . . . . . . . . . . . . . . . . . . . . . . . 
Seal of Bank and Signature(s)

Note:  All italicized text is for guidance on how to prepare this demand guarantee and shall be deleted from the final document.

* The Guarantor shall insert an amount representing the amount of the advance payment in Nepalese Rupees of the advance payment as specified in the Contract.

** Insert the date Thirty days after the expected completion date. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee.

Retention Money Security

(On letterhead paper of the Bank)

............................ Bank’s Name, and Address of Issuing Branch or Office...................................

Beneficiary:	___________________ [Insert name and Address of Employer]

Date:	________________[Insert date of issue]

RETENTION MONEY GUARANTEE No.:	[Insert guarantee reference number]

We have been informed that ________________ [insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture] (hereinafter called "the Applicant") has entered into Contract No. _____________ [insert reference number of the contract] dated ____________ with the Beneficiary, for the execution of _____________________ [insert name of contract and brief description of Works] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, the Beneficiary retains moneys up to the limit set forth in the Contract (“the Retention Money”), and that when at least eighty (80) percent of the whole works have been completed, progress of the works is satisfactory in accordance with the Contract as per approved work schedule and it can be assured that the works can be completed at the intended completion date, payment of [insert the amount of the Retention Money] is to be made against a Retention Money guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of ___________ [insert amount in figures] (                    ) [amount in words]1 upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand,  stating that the Applicant is in breach of its obligation(s) under the Contract, without your needing to prove or show grounds for your demand or the sum specified therein.

This guarantee shall expire no later than the …. day of ……, 2… 2, and any demand for payment under it must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

____________________ 	
[Seal of Bank and signature(s)]

Note:  All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.

BIDDING DOCUMENT

for

THE PROCUREMENT OF

[Insert identification of the Works]

International Competitive Bidding (ICB)

Single Stage: Two-Envelope Bidding Procedure

(PRICE BID)

[Insert the name of Public Entity]

Issued on:

Bid Document issued to:

Contract Identification No:

Table of  Contents

Letter of Price Bid	113

Schedules	115

Bill of Quantities [Unit Rate contract]	115

Schedules of Prices [Lump sum contract]	115

Tables of Adjustment Data	117

Nonadjustable	117

Bill of Quantities	118

Section 6:- Preamble of Bill of Quantities	120

# Letter of Price Bid

The Bidder must accomplish the Letter of Price Bid in its letterhead clearly showing the Bidder’s complete name and address.

Date: .........................................................

Name of the contract: .........................................................

Invitation for Bid No.: .......................................................

To: ……………………………………………………………………………………………………….....

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) Clause 8;

- We offer to execute in conformity with the Bidding Documents the following Works:

(c)The total price of our Bid, excluding any discounts offered in item (d) below is: [Insert one of the options below as appropriate] or when left blank is the Bid Price indicated in the Bill of Quantities

Option 1, in case of single contract:  Total price is: [insert the total price of the Bid in words and figures];

Or

Option 2, in case of multiple lots (contracts): (i) Total price of each lot (contracts):  [insert the total price of each lot in words and figures]; (ii) Total price of subject contract [say Lot1] and Lot2 [another contract] [insert the total price in words and figures]; (iii) Total price of subject contract [say Lot1]and Lot3 [another contract] [insert the total price in words and figures]; Total price of subject contract [say Lot1], Lot2 [another contract], Lot3 [another contract], ………………..[insert the total price in words and figures];

(d) The discounts offered and the methodology for their application for subject contract [single contract] are:…………………………………………….. [For Bidding Documents not provisioning multiple contracts]

Add following if Bidding Document provisions applicability of multiple contracts

The discounts offered and the methodology for their application for subject contract [say Lot1] and Lot2 [another contract] are:……………………………………………..

The discounts offered and the methodology for their application for subject contract [say Lot1] and Lot3 [another contract] are:……………………………………………..

The discounts offered and the methodology for their application for subject contract [say Lot1], Lot2 [another contract] and Lot3 [another contract],……………………, are:……………………………………………..

[Note:

- Formulate possible combinations depending upon the number of lots under Bidding Process and modify accordingly Paragraph (c) and (d)]

- Our bid shall be valid for a period of  [insert validity period as specified in ITB 18.1]  days from the        date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall  remain binding upon us and may be accepted at any time before the expiration of that period;

- If our bid is accepted, we commit to obtain a performance security in accordance with the  Bidding Document;

- We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed;

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive;

- We agree to permit the Employer/DP or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Employer; and

- If awarded the contract, the person named below shall act as our Representative:

Name: .................................................................................................

In the capacity of   .............................................................................
Signed   …………………………………………………………...

Duly authorized to sign the Bid for and on behalf of …………

Date …………………………………………………………....

# Schedules

# Bill of Quantities [Unit Rate contract]

# Schedules of Prices [Lump sum contract]

Schedule of Payment Currencies

For ...........................insert name of Section of the Works

Separate tables may be required if the various sections of the Works (or of the Bill of Quantities) will have local currency requirements. [Insert the names of each Section of the Works].

|  | A | B | C | D |
| --- | --- | --- | --- | --- |
| Name of Payment Currency | Amount of Currency | Rate of Exchange to Local Currency | Local Currency Equivalent C = A x B | Percentage of Net Bid Price (NBP) 100xC NBP |
| Local currency |  | 1.00 |  |  |
| Foreign Currency #1 |  |  |  |  |
| Foreign Currency #2 |  |  |  |  |
| Foreign Currency #3 |  |  |  |  |
| Net Bid Price |  |  |  | 100.00 |
| Provisional Sums Expressed in Local Currency |  | 1.00 |  |  |
| BID PRICE |  |  |  |  |

Note:

- The rates of exchange shall be the selling rates 30 days prior to the deadline for submission of bids published by the source specified in BDS 15.

- Separate tables may be required, if the various sections of the works (or of the Bill of Quantities) will have local currency requirements. The Employer should insert the names of each section of the works.

# Tables of Adjustment Data

Table A - Local Currency

| Index Code | Index Description | Source of Index | Base Value and Date | Bidder’s Local Currency Amount | Weighting range (in %) to be applied | Bidder’s Proposed Weighting |
| --- | --- | --- | --- | --- | --- | --- |
| To be entered by the Employer | Nonadjustable labour fuel Steel Cement Bitumen - - | — | — | — | 15 - - - - - | 0.15 (fixed) |
|  |  |  | Total |  | 1.00 | 1.00 |

Table B - Foreign Currency

Name of Currency:

If the Bidder wishes to quote in more than one foreign currency, this table should be repeated for each foreign currency.

| Index Code | Index Description | Source of Index | Base Value and Date | Bidder’s Currency in Type/Amount | Equivalent in FC1 | Bidder’s Proposed Weighting |
| --- | --- | --- | --- | --- | --- | --- |
| To be entered by the Employer | Nonadjustable | — | — | — |  | A: B: C: D: E: |
|  |  |  |  | Total |  | 1.00 |

Note:

As per GCC 1.1.3.1, "Base Date" means the date 30 days prior to the latest date for submission and completion of the tender

# Bill of Quantities

Notes for Unit Rate Contracts:

Objectives

The objectives of the Bill of Quantities are:

(a)	to provide sufficient information on the quantities of Works to be performed to enable Bids to be prepared efficiently and accurately; and

(b)	when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic valuation of Works executed.

In order to attain these objectives, Works should be itemized in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost.  Consistent with these requirements, the layout and content of the Bill of Quantities should be as simple and brief as possible.

Content

The Bill of Quantities should be divided generally into the following sections:

- Preamble;

- Work Items (grouped into parts);

- Day works Schedule;

- Provisional Sums; and

- Summary.

Preamble

The Preamble should indicate the inclusiveness of the unit prices, and should state the methods of measurement which have been adopted in the preparation of the Bill of Quantities and which are to be used for the measurement of any part of the works.

Work Items

The items in the Bill of Quantities should be grouped into sections to distinguish between those parts of the Works which by nature, location, access, timing, or any other special characteristics may give rise to different methods of construction, or phasing of the Works, or considerations of cost.  General items common to all parts of the works may be grouped as a separate section in the Bill of Quantities.

Day work Schedule

A Day work Schedule should be included only if the probability of unforeseen work, outside the items included in the Bill of Quantities, is high.  To facilitate checking by the Employer of the realism of rates quoted by the Bidders, the Day work Schedule should normally comprise the following:

(a)	A list of the various classes of labor, materials, and Constructional Plant for which basic day work rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the Contractor will be paid for work executed on a day work basis.

(b)	Nominal quantities for each item of Day work, to be priced by each Bidder at Day work rates as bid.  The rate to be entered by the Bidder against each basic Day work item should include the Contractor’s profit, overheads, supervision, and other charges.

Provisional Sums

A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities.  Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary Bill of Quantities.  The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises.  Where such provisional sums or contingency allowances are used, the Contract Data should state the manner in which they will be used, and under whose authority (usually the Project Manager’s).

Summary

The Summary should contain a tabulation of the separate parts of the Bill of Quantities carried forward, with provisional sums for Day work, for physical (quantity) contingencies, and for price contingencies (upward price adjustment) where applicable.

These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the Bidding documents.  They should not be included in the final documents.

## Section 6:- Preamble of Bill of Quantities

Notes on the Bill of Quantities for Unit Rate Contracts

General

1.	The Bill of Quantities shall be read in conjunction with the Instructions to Bidders, General and Particular Conditions of Contract, Technical Specifications, and Drawings.

2.	The quantities given in the Bill of Quantities are estimated and provisional, and are given to provide a common basis for bidding. The basis of payment will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Engineer and valued at the rates and prices bid in the priced Bill of Quantities, where applicable, and otherwise at such rates and prices as the Engineer may fix within the terms of the Contract

3. 	For any item for which measurement is based on records made before or during construction the records shall be prepared and agreed between the Engineer and the Contractor.  Should the Contractor carry out such work without the prior agreement of the Engineer, the Engineer may request the Contractor to carry out investigations to confirm the extent of the work and the quantity of work certified for payment shall be solely at the Engineer’s discretion.  The cost of any such investigation shall be borne by the Contractor.

4.	The rates and prices bid in the priced Bill of Quantities shall, except as otherwise provided under the Contract, include all construction equipment, labor, supervision, materials, erection, maintenance, insurance, profit, taxes, and duties, together with all general risks, liabilities, and obligations set out or implied in the Contract.

5.	A rate or price shall be entered against each item in the priced Bill of Quantities, whether quantities are stated or not. The cost of items against which the Contractor has failed to enter a rate or price shall be deemed to be covered by other rates and prices entered in the Bill of Quantities.

6.	The whole cost of complying with the provisions of the Contract shall be included in the Items provided in the priced Bill of Quantities, and where no Items are provided, the cost shall be deemed to be distributed among the rates and prices entered for the related Items of Work.

7.	General directions and descriptions of work and materials are not necessarily repeated nor summarized in the Bill of Quantities. References to the relevant sections of the Contract documentation shall be made before entering prices against each item in the priced Bill of Quantities.

8.    Provisional Sums included and so designated in the Bill of Quantities shall be expended in whole or in part at the direction and discretion of the Engineer in accordance with the Conditions of Contract.

9.   The method of measurement of completed work for payment shall be in accordance with [Insert the name of a standard reference guide, or specification to be used].

10.	Arithmetic errors will be corrected by the Employer as follows:

(a) 	if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected.

(b)	if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and

(c)	if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic errors, in which case the amount in figures shall prevail subject to (a) and (b) above.

General

Work shall not be executed on a daywork basis except by written order of the Engineer. Bidders shall enter basic rates for daywork items in the Schedules, which rates shall apply to any quantity of daywork ordered by the Engineer. Nominal quantities have been indicated against each item of daywork, and the extended total for Daywork shall be carried forward as a Provisional Sum to the Summary Total Bid Amount. Unless otherwise adjusted, payments for daywork shall be subject to price adjustment in accordance with the provisions in the Conditions of Contract.

Daywork Labor

- In calculating payments due to the Contractor for the execution of daywork, the hours for labor will be reckoned from the time of arrival of the labor at the job site to execute the particular item of daywork to the time of return to the original place of departure, but excluding meal breaks and rest periods. Only the time of classes of labor directly doing work ordered by the Engineer and for which they are competent to perform will be measured. The time of gangers (charge hands) actually doing work with the gangs will also be measured but not the time of foremen or other supervisory personnel.

- The Contractor shall be entitled to payment in respect of the total time that labor is employed on daywork, calculated at the basis rates entered by him in the Schedule of Daywork Rates: 1. Labor. The rates for labor shall be deemed to cover all costs to the Contractor including (but not limited to) the amount of wages paid to such labor, transportation time, overtime, subsistence allowances, and any sums paid to or on behalf of such labor for social benefits in accordance with law of Nepal, as well as Contractor's profit, overheads, superintendence, liabilities and insurance and allowance to labor, timekeeping and clerical and office work, the use of consumable stores water, lighting and power; the use and repair of stagings, scaffolding workshops and stores portable power tools, manual plant and tools; supervision by the Contractor's staff, foremen and other supervisory personnel; and charges incidental to the foregoing. The rates shall be stated in the local currency, and paid in Nepalese Rupees.

Daywork Materials

The Contractor shall be entitled to payment in respect of materials used for daywork (except for materials for which the cost is included in the percentage addition to labor costs as detailed heretofore), at the rates entered by him in the Schedule of Daywork Rates: 2. Materials and shall be deemed to include overhead charges and profit as follows;

(a) 	the rates for materials shall be calculated on the basis of the invoiced price, freight, insurance, handling expenses, damage, losses, etc., and shall provide for delivery to store for stockpiling at the Site. The rates shall be stated in local currency but payment will be made in the following currency proportions:

(i)	foreign: 	percent	[The bidder shall state the percentage in a common foreign currency equivalent required for payment and the exchange rates and official sources used]

(ii) 	local: 	percent  [To be stated by bidder].

(b) the cost of hauling materials for use on work ordered to be carried out as daywork from the store or stockpile on the Site to the place where it is to be used will be paid in accordance with the terms for Labor and Constructional Plant in this Schedule.

Daywork Contractor's Equipment

- The Contractor shall be entitled to payments in respect of Contractor's Equipment already on Site and employed on daywork at the basic rental rates entered by him in the Schedule of Daywork Rates: 3. Contractor's Equipment. The said rates shall be deemed to include due and complete allowance for depreciation, interest, indemnity and insurance, repairs, maintenance, supplies, fuel, lubricants, and other consumable, and all overhead profit and administrative costs related to the use of such equipment. The cost of drivers, operators and assistants will be paid for separately as described under the section on Daywork Labor.

- In calculating the payment due to the Contractor's Equipment employed on daywork, only the actual number of working hours will be eligible for payment, except that where applicable and agreed with the Engineer, the traveling time from the part of the Site where the Construction Plant was located when ordered by the Engineer to be employed on daywork and the time for return journey thereto shall be included for payment.

  - The basic rental rates for Contractor's Equipment employed on daywork shall be stated in local currency but payments to the Contractor will be made in currency proportions as follows:

i. foreign: 	percent	[To be stated by bidder. The bidder shall state the percentage in a common foreign 	currency equivalent required for payment and the exchange rates and official sources used]

ii. Local: percent	[To be stated by bidder].

Provisional Sums

A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities. Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary Bill of Quantities. The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises. Where such provisional sums or contingency allowances are used, the PCC should state the manner in which they will be used, and under whose authority (usually the Project Manager’s).

The estimated cost of specialized work to be carried out, or of special goods to be supplied, by other contractors should be indicated in the relevant part of the Bill of Quantities as a particular provisional sum with an appropriate brief description. A separate procurement procedure is normally carried out by the Employer to select such specialized contractors. To provide an element of competition among the Bidders in respect of any facilities, amenities, attendance, etc., to be provided by the successful Bidder as prime Contractor for the use and convenience of the specialist contractors, each related provisional sum should be followed by an item in the Bill of Quantities inviting the Bidder to quote a sum for such amenities, facilities, attendance, etc.

- The Bill of Quantities shall be read in conjunction with the Instructions to Bidders, Bid Data Sheet, General Conditions, Conditions of Particular Application, Standard Specification, Special Provisions to the Standard Specifications, Appendices to Special Provisions and the Drawings.

- The quantities given in the Bill of Quantities are estimated and provisional, and are given to provide a common basis for bidding. The basis of payment will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Engineer and valued at the rates and prices tendered in the priced Bill of Quantities, where applicable, and otherwise at such rates and prices as the Engineer may fix within the terms of the Contract.

- For any item for which measurement is based on records made before or during construction the records shall be prepared and agreed between the Engineer and the Contractor.  Should the Contractor carry out such work without the prior agreement of the Engineer, the Engineer may request the Contractor to carry out investigations to confirm the extent of the work and the quantity of work certified for payment shall be solely at the Engineer’s discretion.  The cost of any such investigation shall be borne by the Contractor.

Bill of Quantities

[Insert Bill of Quantities]

“GoN” word indicates all public entities according to Public Procurement Act, 2063

Substitute “contracts” where bids are called concurrently for multiple contracts. Add a new para. 2 and renumber paras 2 - 9 as follows: "Bidders may bid for one or several contracts, as further defined in the Bidding Document. Bidders wishing to offer discounts/cross discounts in case they are awarded more than one contract will be allowed to do so provided those discounts are included in the Letter of Bid.”  The paragraph two shall provide qualification requirement of a bidder for each contract if bidding process comprises of more than one contract (multiple contract).

A brief description of the type of work shall be provided including quantities of major works, location of the project and other information necessary to enable potential bidders to decide whether to respond to the invitation, a Bidding Document requires bidders to have specific experience and capabilities and therefore also be included in this paragraph.

The time interval between last purchasing date and last submission date shall not be more than one day.

If pre-bid meeting shall not be held delete this para and renumber other paras.]

[Procuring Entity can insert other mandatorily required information as per Clause 49KA of PPR. If not required delete this paragraph.]

There is no limit on number of running contracts that a bidder can have for bidders participating as JV with maximum share 25 % and not having singed more than two (2) contracts for works of similar nature since 2078-12-03 i.e. March 17, 2022 in Nepal

Note: (1) Only the contracts accepted since 2078-12-03 i.e. March 17, 2022 which are not substantially completed are considered. The contracts those are running under any type of foreign assistance are not accounted for this purpose.

(2) This criteria is not applicable for bidders participating as JV with maximum share 25 % and not having singed more than two (2) contracts for works of similar nature since 2078-12-03 i.e. March 17, 2022 in Nepal.

Liquid Assets mean cash and cash equivalents, short-term financial instruments, short term available-for-sale-securities, marketable securities, trade receivables, short-term financing receivables and other assets that can be converted into cash within ONE YEAR.

Use one of the two options as appropriate.

Note: Except contracts accepted and running under any type of foreign assistance, all the contracts accepted and running since 2078-12-03 i.e. March 17, 2022 which are not substantially completed needs to declare.

Only the contracts accepted since 2078-12-03 i.e. March 17, 2022 are to be mentioned.

In lump sum contracts, delete “Bill of Quantities” and replace with “Schedule of Activities” throughout this section.

1	The Guarantor shall insert the amount of the Retention Money.

2	Insert the same expiry date which is 30 days more than the end of Defect Liability Period.  The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee.

In lump sum contracts, delete “Bill of Quantities” and replace with “Schedule of Activities” throughout this section.